## Sheet1
Climate Screening Tools, Data and Approaches |  |  | 2015-12-17
Actions | Responsible | Deadline | Status
Develop working draft of sub-working group workstreams and milestones. | All | 2014-12-18 | Draft
Share guidance documents: chapau and ToR for overall working group TOR |  | 2014-12-19
Faciliate collaboration: establish work site on USAID web-based platform, and provide access to sub-working group | Mike Colby | 2014-12-19
Develop/share draft definitions of key terms for group review. | Jon Randall | 2014-12-19
Understand current agency practices: Share USGRP analysis of current agency practices and consider whether any additional analysis is required | USGRP | 2014-12-19
Discussion on data: hold dedicated teleconference on data and information needs, lead by science agencies and programs. |  | TBD
Sub-working group meeting to: - Finalize definitions of key terms - Agree on general workstgreams and milestones for CY15 - Review current donor practices (USG + donors) and lessons learned. |  | 2015-01-14
USG - World Bank to discuss: (1) Key findings, challenges and lessons gleaned from multi-donor collaborations; (2) the WBG’s screening tool and the environment in which it operations. |  | TBD (early 2015)
Draft
Done