Final Evaluation of the Botswana

Natural Resources Management Project

(690-0251)

FINAL DRAFT

Presented to

United States Agency for International Development/Botswana

under contract no. LAG-4200-1-00-3056-00

Presented by

Tropical Research & Development, Inc.

November 1996

Acronyms and abbreviations

AID/W		Agency for International Development/Washington

BWTI			Botswana Wildlife Training Institute

CAMPFIRE		Communal areas Management Project for Indigenous Resources

CBO			Community-based organization

CBNRM		Community based natural resource management

CECT			Chobe Enclave Conservation Trust

CDD			Curriculum Development Division in the Ministry of Education

CORDE		Cooperative for Research and Development

CWT			Chobe Wildlife Trust

DLUPU		District Land Use Planning Unit

DOD			District Officer (Development)

DOL			District Officer (Lands)

DTI			Domestic Technology International

DWNP		Department of Wildlife and National Parks

EC			European Community

EEC			European Economic Community

FONSAG		Forum for NGOs in Sustainable Agriculture

GOB			Government of Botswana

IMC			Inter-ministerial Coordinating Committee

IUCN			World Conservation Union

KCS			Kalahari Conservation Society

KDT			Kuru Development Trust

M&E			Monitoring and Evaluation

M&U			Management and Utilization Division, DWNP

MCI			Ministry of Commerce and Industry

MFDP			Ministry of Finance and Development Planning

MLGLH		Ministry of Local Government, Lands and Housing

MOA			Ministry of Agriculture

MOE			Ministry of Education

NCS			National Conservation Strategy

NGO			Non-governmental Organization

NORAD		Norwegian Agency for International Development

NRMP		Natural Resources Management Project

PAC			Problem Animal Control

PRA			Participatory Rural Appraisal

PTTC			Primary Teacher Training College

SADC			Southern African Development Community (formerly SADCC)

SARP			Southern African Regional Program

SIAPAC		Socio-Economic Impact Assessment and Policy Analysis Corporation

SNV			Netherlands Development Organization

WMA			Wildlife Management Area

Project Identification Data Sheet

Country		Regional - Botswana Subproject

Project Title		Natural Resources Management Project

Project Number	690-0251.33

Project Dates

First Project Agreement:				August 29, 1989

Final Obligation Date:				Fiscal Year 1996

Most recent Project Assistance Completion Date:	August 31, 1997

Project Funding (amounts obligated to date)

AID Bilateral funding:				U.S. $19,900,000

Other Major donors:					U.S. $      0

Host Country Counterpart funds:			U.S. $ 5,500,000

TOTAL							U.S. $25,400,000

Mode of implementation

Institutional contract:			Chemonics International

Subcontractors:			Conservation International

Domestic Technology International

Support grants to PVO/NGOs

Cooperative Agreement		PACT

Responsible Mission Officials

Mission Director:			Valerie L. Dickson-Horton

Project Officer:			Robert McColaugh

Previous evaluations			Midterm Evaluation, July 1993

Supplementary data

Project agreement signed:		8/21/89		$5.4 million

Amended				1/18/90		 3.5 million

9/24/93		 5.5 million

9/30/94		 5.5 million

FINAL DRAFT

NATURAL RESOURCES MANAGEMENT PROJECT

FINAL EVALUATION

Executive Summary

Throughout Africa, during the last 10-15 years, conservationists have been developing approaches to link conservation with development.  The hypothesis was that by allowing fuller participation of communities in natural resource management and providing for their development needs, positive impacts on the conservation of a particular resource or protected area would be achieved.  Most of these Integrated Conservation and Development Projects substituted resources lost due to the protection of an area on farms (e.g. agro-forestry), gave people only limited, or no,  access to the protected resources and, at the same time,  tried to increase their participation in the management of these resources. Incentives for participation were limited because, at the end of the day, communities have lost access to resources that their livelihoods depended on.

In Botswana, the United States Agency for International Development (USAID) and the Government of Botswana have been supporting the Natural Resources Management Project (NRMP) since 1989.  NRMP is actively promoting community capacity to manage their own natural resources, not by substituting  natural resources on the farm, but through real economic returns based on the communities’ use of resources.  This focus on enterprise development has provided incentives for communities to not just participate in natural resource management, but to take responsibility over their resources and economic development.  In Botswana, this approach is called community based natural resource management, or CBNRM, and has attracted considerable interest among a wide range of donors, government agencies and officials and within the communities themselves as a vehicle towards diversifying the rural economy, while maintaining or improving the environment.

The Botswana component of the Natural Resource Management Project, funded by USAID as part of its assistance to SADC region which aims to promote sustainable, conservation-based development on lands that are marginal for crop production and domestic livestock.  In its work towards CBNRM the NRMP had the following set of goals, purposes and objectives:

Goal:		Increase incomes and enhance capability to meet basic human needs through sustainable utilization and conservation of natural resources, particularly wildlife.

Subgoal:	Promote sustainable development of communities on lands that are marginally suitable for agriculture

Purposes:

1.	To demonstrate, through practical examples, the technical, social, economic, and ecological viability and replicability of community-based natural resources management and utilization programs on marginal lands for increasing household and community income while sustaining natural resources.

2.	To improve national and local capability to halt the decline in the wildlife resources base through training, education, protection, communication and technology transfer.

Objectives:

1.	To demonstrate that sustainable natural resources utilization is a profitable and viable development option for rural communities

2.	To increase local employment and incomes through diversifying employment opportunities in the sustainable utilization of natural resources.

3.	To strengthen local institutional decision making and management units so as to empower them to become self-sufficient managers of their local resources.

4.	To improve the participation and role of women in resources management programs, thereby improving their incomes.

5.	To strengthen staff training and career development for employees of the Department of Wildlife and National Parks.

In 1993 a mid-term evaluation was conducted for the NRMP that, inter alia, recommended an additional component to the project to support non-governmental organizations.  This resulted in the formation of the Institutional Reinforcement for Community Empowerment (IRCE) component with the following additional objectives:

1.	Capacity building for non-governmental organizations to empower communities to manage their natural resources in a sustainable manner.

2.	Development of a grants mechanism to support community-based natural resource management/utilization projects.

The NRMP consists of six components to achieve the above seven objectives, aimed at developing the capacity within governmental and non-governmental organizations to facilitate CBNRM:

(A) 	Demonstration projects in community based resource utilization predicated on defining the resource base as a community asset.  Community based projects are based on wildlife utilization through tourism, hunting, processing and marketing of animal products, and the sustainable utilization of veld and forest products.

(B)	Planning and applied research to support the development of management plans for the northern national parks and reserves, and for the national network of Wildlife Management Areas (WMAs).  The impact of project activities is also monitored under this component.

( C)	Environmental Education activities to increase public awareness of environmental 	issues through curriculum development, teacher training, and non-formal education.

(D)	Personnel planning and training activities to strengthen DWNP’s institutional capacity. Outputs focus on establishing a Human Resource Development Unit and an effective training program at the Botswana Wildlife Training Center.

(E)	NGO and CBO support activities to develop their capacity so that the communities themselves may implement CBNRM.

(F)	Policy support to Government aimed at contributing to the enabling environment within the Botswana legal and regulatory structure affecting CBNRM.

USAID funded the project in August 1989.  The present grant completion date in 31 August 1997.   This final evaluation is intended as a tool to plan for the completion of the Project, with NRMP implementors and evaluators jointly reviewing the Project’s objectives and expected outputs.  The scope of work for this final evaluation is to answer three basic questions:

1.	Has the project had the results for which it was intended?  If not, why?

2.	What project activities and results will yield significant local impacts and provide models for regional application?

3.	What activities have not achieved the anticipated results or could have significantly greater impact if continued beyond the current PACD?  How should this be accomplished?

Demonstration projects in community based resource utilization

Through its demonstration projects the Project is working in over 50 separate villages or settlements and assisting in the range of 50,000 people.  Demonstration projects fall under three main categories of resource utilization: consumptive use of wildlife and veld products, and; non-consumptive (mostly photographic tourism).  With the exception of Khwai, all the current community based consumptive wildlife projects are earning part of their income from photographic tourism.  Through IRCE,  the project has provided capacity building support to ensure broad based benefits, transparency and sustainability of activities.

Community groups or trusts have not yet matured to the point where they have all the necessary skills to both continue projects and ensure community involvement. Continued support from the project must be maintained to take community trusts from the start-up organizing stage through the establishment of routine administration of on-going projects and ability to fund and implement secondary projects from benefits received.

In this context, the project should continue to emphasize capacity building and planning within the districts for community based natural resource management.  This will help ensure that community activities become part of the country’s planning process and ensure some technical input into specific project activities.

While DWNP and project staff have a long-term vision of the benefits of CBNRM and potential uses of profits - the community themselves must develop a vision.  The project should assist the community to develop a vision of where their community would be in the future - 20 or more years.  This vision will help them work towards a common goal and provide insight on priorities for investment of funds earned by the Trust.

Procedures for distribution of benefits have not yet been worked out and the project should start to focus on how community profits can be used to start new opportunities.  This reinvestment in new opportunities will increase the number of income generation projects and employment creation activities. The project should assist the trusts to develop general guidelines for procedures for benefit distribution from the trusts.  The general guidelines should be adapted and adopted by each separate trust.

The wide array of possible resource uses, evidenced in the projects activities, shows the potential veld resources hold for diversifying the rural economy.  The interest of other communities to duplicate activities of the Chobe Enclave Conservation Trust is building a momentum for CBNRM and speaks well for the sustainability of the project.  A wind down of project activities at this point may slow the momentum, reduce the rate of return on the investment and cause a loss of confidence within the communities. This potential loss of confidence will also make it difficult for government and other donors to pick up project activities. To the contrary, the NRMP should encourage this momentum effect by increasing the number of community-based projects, number/range of resources utilized and maximizing the number of spinoff activities from main activities.  This will entail further integrated planning among sectors and partners.

Planning and applied research

A total of ten management plans have been developed for National Parks and Wildlife Management Areas.    Development of the management plans provided a good opportunity for building the capacity of DWNP staff to identify management problems and options for their solution.  Moreover, the process provided an opportunity to determine best development options for a specific area.  The management plans should be further adapted to the normal evolution of protected area development and management by the Department of Wildlife and National Parks

However, the Wildlife Management Area (WMAs) do not yet have regulations to guide the exercise of authority.  In the absence of regulations, contravention in gazetted WMAs go unchallenged.  Several WMAs, particularly those in Kgaligadi District are not gazetted and are lacking implementation of the management plans. The development of WMA regulations require wide consultation within government and the resident populations.  In order for CBNRM to be sustainable in these areas,  the Project should emphasize the operationalization of Wildlife Management Areas and their management plans and support to establishing effective regulations.

The monitoring and evaluation component of NRMP provides a good mechanism for understanding the social and economic processes that shape how people use natural resources. The information being collected can be used as a planning tool by DWNP, other organizations and agencies with CBNRM implementation responsibilities, and the community organizations themselves. The information being collected by NRMP’s monitoring and evaluation component also will permit testing and refining basic assumptions and hypotheses of CBNRM.

The sustainability of the system within DWNP and its continuing utility as a planning and management tool to support national implementation of CBNRM will depend on DWNP adequately staffing its sociology office, and doing so soon enough to permit the people hired to acquire necessary skills and understanding before BNRMP departs.

Environmental Education

Environmental education is a topic that in the past has traditionally fallen outside of the formal curriculum in most countries.  Integration and awareness building are long-term processes (10-20 years) that require coordination and dedication by a wide array of professionals including teachers, publishers, curriculum development specialists, NGOs, government planners and natural resource professionals.  The mid-term evaluation of the NRMP recognized that focusing on the integration of environmental education within the curriculum was a necessary, but slow, meticulous process that would take many years to yield visible results to support CBNRM activities.  Within the NRMP, a tremendous number of environmental education activities were tried based on strategies that have been used successfully in environmental education campaigns internationally.  SIDA is now providing environmental education assistance to the Ministry of Education.  The original vision of the scope of work for the Environmental Education advisor and the Ministry of Education included a breadth and depth of activities that far exceeded the time frame and personnel available for implementation and follow-through.  Sustainability at the original level of effort is clearly not possible, nor is it necessarily needed as participating organizations re-adapt the methods to fit their circumstances.

In response to recommendations of the project's mid-term evaluation, a non-formal education advisor was recruited in October 1995 to build the capacity within the Conservation Education Division of DWNP to design and disseminate educational materials at a national scale on the departments new policies and practices.  This effort was seen as complementary to environmental education activities within the Ministry of Education and viewed as strategic support for CBNRM/CBOs at the district and community level in the rural areas.  In nine months, the team has been extremely effective in reaching critical stakeholders with relevant materials.

A vibrant, but skeletonal staff has had a tremendous direct impact for CBO/CBNRM publicity and clarification of steps towards implementation of CBNRM concepts. They are currently called from all over the country with requests for information. To date, due to limited human resources, they have been concentrating in the southern and western areas of the country.  The initial strategy has focused on awareness-building and knowledge of policies first for DWNP staff followed by workshops with district leaders, teachers as well as NGO and CBO representatives.

Currently, there are insufficient staff to meet the demands placed on the unit for development of materials, design and implementation of workshops, critical follow-up visits to support district officials and NGOs, and training for DWNP officers on policy issues.  Given the high demand and need for these activities, there must be a corresponding increase in budget allocations from DWNP for workshops and materials as well as more staff seconded to the unit.

Future activities should continue to target audiences that are known to have a multiplier effect (i.e. NGOs, teachers, DWNP staff, District officials), however quick extension follow-up is needed to maintain momentum. Networking with NGOs and the formal education sector has thus far been very successful to overcome constraints of the government sector for quick, efficient responses. Strategic networking with selected organizations will continue to foster sustainability of the effort.

Personnel planning and training

The combined coordination of the Human Resources Development Unit with the Botswana Wildlife Training Institute has resulted in a substantial restructuring of DWNP towards personnel training and capacity-building.  Appropriate training has been systematically provided for non-certificated tenured staff (with some limitations due to DPSM regulations) and new recruits through a comprehensive Induction and Basic Training program and selective pre-service training).  A new revised national certificate program is underway, but some concerns must be addressed in order for the program to effectively meet the needs of the department.  Namely, the length of time required to complete the program in relation to the number of people who need training creates a bottleneck, lack of appropriate logistical arrangements by support staff seriously undermine the training effort, and collaboration with supervisors for on-the-job application of skills during the field projects need further attention.

Educational enhancement, career path alignment and the development of specialized in-service training are key areas for further concentration of efforts which require coordination by BWTI staff, Conservation Education and Community Extension units with HRDU.  The Conservation Education unit's programs in conservation policy have provided critical policy information to district offices using innovative methods. The development of a Problem Animal Control Unit which included selective recruitment, training of instructors, transition of responsibility for program implementation to qualified Batswana counterparts from the advisor and successful training of DWNP game scouts as PAC officers.  There is a clear trend in all training components towards a transition in responsibilities from NRMP advisors to DWNP staff which is critical for sustainability of the programs.  Procedures are needed within DWNP for continued institutional support of such programs.

Constraints in implementing the Personnel Planning and Training effort included high turnover rates of personnel within DWNP and DPSM, frequent post changes, training and delays in assignment of counterparts, incompatibility of proposed HRD strategies with DPSM procedures and non-implementation of compatible HRD techniques by certain DWNP administration staff.

Future activities as identified by DWNP’s Administration unit as priorities include: a) skills transfer on management and use of computerized personnel records and implementation of performance standards for job descriptions, b) design and implementation of department training plan and c) team building within the Administration unit towards creating a service orientation.

There has been a complete transformation of the facilities at BWTI, quality and focus of training effort and capacity of instructors.  Curriculum revision was a participatory process involving all levels within DWNP.  Professionals within DWNP see BWTI as an institute that is playing a critical role in raising the performance standards of the department.  An evaluation of on-the-job application of skills is currently under review via face-to-face interviews and questionnaires completed by supervisors and IBT graduates.   Success of the training will be undermined if supervisors at the districts do not support the application of the newly acquired skills on the job.  However, institutional mechanisms are critically needed to support skills application or the program will not meet its objective of upgrading the capability of the department.

NGO and CBO support

The midterm evaluation challenged several flaws in the original project design.  Namely, that replicable and transferable models of CBNRM existed and that NGOs were in a position to implement all facets by mobilizing communities, transferring NRM technology, facilitating mutually beneficial arrangements with outside stakeholders and to using new policy changes to generate income through sustainable natural resource management.  Given that neither the technology itself nor a viable technology transfer mechanism existed, the mid-term evaluators recommended that a flexible funding mechanism be put in place to facilitate CBNRM activities, technical and institutional capacity for CBNRM be strengthened, and the demonstration projects should be viewed as experimental with the goal of developing an array of approaches that could be achieved, replicated and sustained.

Several mechanisms are possible to ensure service supported CBNRM activities.  Community-based organization could manage primarily on its own and/or build partnerships with district officials, NGOs, private enterprise or DWNP and other ministries for marketing channels, advocacy, technical assistance or capacity-building training.  Where CBOs have not yet developed or where community processes are weak or subverted due to marginalization, it may be necessary for rural-based NGOs with a grassroots focus  to work with communities as partners to develop CBNRM structures and enterprises.  However, this may lead to a dependency relationship rather than empowerment which would further disenfranchise the communities.

Another strategy being pursued by the Project to insure sustainability of CBNRM activities is the formation of a CBO network.  There is clearly potential for a more formalized structure, but care must be taken that the network does not become an end in itself, that it does not take on a life of its own which becomes more important than the goals of the individual CBO members and that their capacity is not diverted from their primary goals. Such a CBO network will have a grassroots constituency and negate the need for communities to have NGOs or other organizations act as “gatekeepers” to the community.

IRCE developed a participatory tool, Operational Capacity Assessment Tool (OCAT) to assess organizational development and identify where organizations sit on a continuum from nascent to mature.  To date, eleven NGOs have opted to utilize the OCAT to set goals for organizational capacity enhancement and to track progress towards their achievement.   IRCE should encourage those NGOs who find the OCAT tool useful to undertake OCAT assessments on a regular basis to track their progress.  Throughout this process it should be born in mind that OCAT is a instrument designed for rapid participatory assessment needs to continually be revisited to ensure that organizations are on tract.   This process should be adapted for community based organizations as a way to track their progress towards institutional maturity.

While the NGO community has many skills (both technical and organizational) many are not focused on building community capacity to manage their natural resources, in addition they are constrained by lack of staff and financial resources. Several NGOs have skills to offer with respect to production and utilization of resources, conservation and marketing which should be built upon.  As the NGOs develop organizationally they will be defining their mandates and capacities and may move into more community based initiatives.

IRCE must stay focused on the goal of increasing communities capabilities for self management. In this context it is recommended that resources within IRCE should be administratively separated into three components: capacity building for CBOs; grants for supporting CBNRM activities; and, capacity building for NGOs.  This will help clarify activities meant for long-term capacity building for NGOs and direct capacity building to the communities.

Policy support

The policy component of the project is part of the package of activities recommended in the mid-term evaluation. The project had been working on departmental policy before this with such activities as drafting guidelines for community activities and the guidelines for joint ventures.  Within the past year, two major policy initiatives have occurred.  The first,  the NGO Task Force for Conservation in Botswana is a grouping of NGOs that have come together to support efforts to reverse declines in the nation’s wildlife and to help achieve greater recognition of the role that wildlife, and its conservation, can play in the national life of Botswana.  The second, a policy review on community based natural resource management, will assist in the development of  a coherent community based natural resource management policy statement for review and approval by government.

Further policy work is needed to address the sustainability of CBNRM and ensure that services are provided to the communities.  More resources are needed at the district and sub-district level for policy knowledge and awareness building such as a set of district institutional guidelines.  Other guidelines such as trust formation, benefits distribution, or accountability may be needed.   Additional policy work is needed to develop regulations for the management of Wildlife Management areas.  The project should also direct increasing attention the open access question of veld resources so that communities have more ownership over the resources they depend. Finally, the project should continue to assist DWNP and other policy stakeholders to complete the process of consensus building, amendment, adoption and implementation of the CBNRM policy document currently under preparation.

The project has had substantial and fundamental impacts on multiple levels.  At the regional level, it provided opportunities for government officials in Botswana to have a common ground on which to exchange ideas on working in partnership with communities with other countries in the region.  It has facilitated the exchange of experiences on national policy, and it has supported the exchange of ideas amongst the rural populations of a number of countries and exposed Batswana to training opportunities in other countries.  Moreover, it has provided viable community based natural resource management models that can be transferred or replicated within the region.

At the national government level,  it has contributed to joint efforts between various ministries and other Government of Botswana services towards increasing support for community- based natural resource management.

At the community level it has been instrumental in forging a new partnership between the GOB and communities, in allowing communities and community members to see the advantages of working together, and in providing the opportunity for the private sector to form private partnerships with communities.

At the level of the private sector, it may contribute to the establishment of standards by which the private operators deal with CBO’s and lead to joint venture partnerships that will increase communities incomes.

In light of the above progress and the potential for a greater rate of return on present investment the following general recommendations are being put forward to the Government of Botswana and USAID for their consideration:

1.	Considering NRMPs excellent progress to date and substantial contributions to the regional strategic objectives, the evaluation team feels strongly AID should consider a long term commitment (5 years or more) to community-based activities.   This will capitalize on the investment by GOB and USAID.

2.	In this context, it is recommended that the project continues with minor adjustment for two additional years, during which a new design for a follow on activity based on community actions should be completed.  Current capacity-building activities will allow for follow on activities in other sectors and should be taken advantage of.  The value added to existing project activities given an extension are outlined in annex 1.

3.	There should be a shift in responsibilities for implementation of activities from the NRMP advisors to their counterparts and other DWNP staff as soon as possible.  This requires DWNP to appoint appropriate, qualified counterparts and to budget appropriately.

4.	During the two year extension greater emphasis should be given to capacity-building at the district level for CBNRM.  To fully accomplish this DWNP should hire additional staff to fill the district community liaison positions and NRMP management should consider opportunities to ease logistical constraints i.e housing closer to the communities.

5.	The NRMP main contractor should provide overall monitoring of CBNRM replication and spin off  activities within the project since they have a broader perspective and a wider range of technical staff. USAID needs to develop a memorandum of understanding to the above effect

Final Evaluation of the Botswana Natural Resources Management Project

FINAL DRAFT

Table of Contents

Acronyms and abbreviations	ii

Project Identification Data Sheet	iii

Executive Summary	iv

1.0	Introduction	1

1.1	Evaluation purpose and statement of work	2

1.2	Team composition	2

1.3	Methodology	3

2.0	Strategic overview	3

2.1	Socio-economic context in Botswana	3

2.2	USAID structural re-organization	5

2.3	Botswana Policy and Institutional Environment	5

2.4	The Regional Natural Resources Management Project	6

2.5	The Botswana Natural Resources Management Project 	6

2.6	Mid-term evaluation	8

2.7	Other donor involvement 	10

3.0	Response of implementing agencies: review of project activities & components	11

3.1	Policy development and institutional capacity-building	11

3.1.1	Background	11

3.1.2	Key elements and progress to date	12

3.2	Planning and Research	16

3.2.1	Background	16

3.2.2	Key elements and progress to date	17

3.3	Community-based resources utilization: demonstration projects	25

3.3.1	Background	25

3.3.2	Key elements and progress to date	25

3.4	NGOs involvement in Community-based Natural Resource Management	33

3.4.1	Background	33

3.4.2	Key elements and progress to date	34

3.5	Personnel Planning and Training Component	40

3.5.1 Background	40

3.5.2 Key Elements and Progress to Date	41

3.6	Formal and Non-formal Environmental Education	47

3.6.1	Background of Formal Environmental Education Activities	47

3.6.2 	Key Elements and Progress to Date	48

3.6.3 Background of Conservation Education Activities	51

3.6.4 Key Elements and Progress to Date	52

4.0 	Impacts of the Natural Resource Management Project	57

4.1	Community Empowerment	57

4.2	Policy and Institutional Impacts	58

4.3	Economic impacts	59

4.5	Regional Impacts	61

4.6	Impacts on Small and Medium Enterprises	62

4.7	Gender	63

5.0	Project Management Issues	64

5.1	Contractor Performance	64

5.2	USAID/RCSA Performance	65

5.3	Partner Participation	66

5.3.1	Department of Wildlife and National Parks	66

5.3.2	Non-government organizations	66

5.3.3	Other partners	67

6.0	Financial Implications of Evaluation Recommendation	67

7.0	Post evaluation considerations and action recommendations	69

8.0	Lessons Learned	69

Annex 1:  Value Added and Constraints to Project Componets with an Extended PACD	71

Annex 2: Macro and Micro Economic Analysis	75

Annex 4: Partial List of Contacts	83

Annex 5:  Selected References	85

1.0	Introduction

Throughout Africa, during the last 10-15 years, conservationists have been developing approaches to link conservation with development.  The hypothesis was that by allowing fuller participation of communities in natural resource management and providing for their development needs, positive impacts on the conservation of a particular resource or protected area would be achieved.  Most of these Integrated Conservation and Development Projects substituted resources lost due to the protection of an area on farm (e.g. agro-forestry), gave people only limited, or no,  access to the protected resources and, at the same time,  tried to increase their participation in the management of these resources. Incentives for participation were limited because, at the end of the day, communities have lost access to resources that their livelihoods depended on.

In Botswana, the United States Agency for International Development (USAID) and the Government of Botswana have been supporting the Natural Resources Management Project (NRMP) since 1989.  NRMP is actively promoting community capacity to manage their own natural resources, not by substituting  natural resources on the farm, but through real economic returns based on the communities use of resources.  This focus on enterprise development has provided incentives for communities to not just participate in natural resource management, but to take responsibility over their resources and economic development.  In Botswana, this approach is called community based natural resource management, or CBNRM, and has attracted considerable interest among a wide range of donors, government agencies and officials and within the communities themselves as a vehicle towards diversifying the rural economy, while maintaining or improving the environment.

This chapter identifies the goals, member and methodology of the evaluation.  Chapter two of the this report commences with a strategic overview of the institutional, policy and socio-economic context in which the project operates.  This includes the socio-economic context in Botswana, policy and institutional environment and general descriptions of the regional Natural Resource Management Project and the Botswana component of that project.

Chapter three details key elements and progress to date, conclusions and recommendations for each of the major project components:  policy development and institutional capacity building; monitoring and evaluation, planning and research; demonstration projects for community-based resource utilization; strengthening of NGO capacity; personnel planning and training, and; formal and non-formal education.

Chapter four highlights the impact the project has made, or may potentially have, for community empowerment, policy, rural economies, environment, enterprise development and gender.

Chapter five discusses various project management issues and makes recommendations where management could be strengthened.  The document ends with a list of post-evaluation action recommendations (Chapter Seven) and lessons learned (Chapter Eight).

1.1	Evaluation purpose and statement of work

The Botswana portion of the regional natural resources management project (NRMP) evaluated in this report is an AID funded project assisting the Government of Botswana to promote sustainable, conservation-based development on lands that are marginal for crop production and domestic livestock.

This final evaluation is intended as a tool to plan for the completion of the Project, with NRMP implementors and evaluators jointly reviewing the Project’s objectives and expected outputs.  In this document the Botswana portion of the regional project is referred to as the NRMP.

The Scope of Work for the evaluation is found in annex x. Generally, the purposes of  this final evaluation of the Botswana subproject are to answer three basic questions:

1) 	Has the project had the results for which it was intended?  If not, why?

2)	What project activities and results will yield significant local impacts and provide models for regional application?

3)	What activities have not achieved the anticipated results or could have significantly greater impact if continued beyond the current PACD?  How should this be accomplished?

1.2	Team composition

The evaluation team consisted of six individuals:

Peter C. Trenchard - Team leader and rural development specialist.  Sixteen years experience 	in community conservation, natural resource management, park planning, natural resource policy, project design and evaluation in Uganda, Burundi, Rwanda, Central African Republic.

George E. Karch -Policy and Economics wizard Ed Karch. Thirty years experience in NRM 	policy, resource economics, agroforestry, small enterprise development, project design and evaluation, in Africa, Central America, and the Caribbean. Peace Corps Senegal. M.Sc. California Polytechnic State University, San Luis Obispo.

Anne Todd Bockarie, Ph.D. Training, Curriculum Development and HRDU specialist,   Curriculum Development Specialist at the University of Florida, Gainesville where doctoral work was completed in Forestry Extension.  An applied forestry and natural resources scientist with ten years experience specializing in community extension and technical training design, delivery and evaluation in Africa, Latin America, the United States and the Caribbean.  Agricultural and natural resources training implemented with USAID, USDA, JADF, OTS, NCAE, Peace Corps, MERGE, AWF, WCI and WWF.

Mike McGahuey - Natural Resources Management Policy Analyst/Monitoring and Evaluation.  	Natural Resources Management/Sustainable Agriculture Advisor, USAID Africa Bureau (AFR/SD/PSGE).

Ruth Buckley - Operational Development of NGOs and CBO Specialist.  USAID/Regional 	Economic Development and Support Office,  Nairobi.

Disikalala M. Gaseitsiwe. Natural Resource Program/Project Specialist.  Senior Planning 	Officer, Ministry of Commerce and Industry, Gaborone.

1.3	Methodology

This evaluation used standard evaluation techniques including key informant interviews, site visits, beneficiary interviews, document review and financial analysis.  The team followed guidelines in the Supplement of Chapter 12, AID Handbook 3, Project Assistance, entitled “AID Program Design and Evaluation Methodology Report No. 7.”

Three team members met in Washington, D.C. to hold discussions with organizations associated with the project including Chemonics International, PACT, World Resources Institute and USAID.    The full team met in Gaborone on 20 October, 1996.  The first three days in Gaborone included initial briefings by Department of Wildlife and National Parks, project and AID staff.  Additional insights were obtained through meetings with other donors and with representatives from the Ministries of Agriculture (MoA), Education (MoE), Local Government, Lands and Housing (MLGLH) and the Ministry of Finance and Development Planning (MFDP)

The team then split into three separate groups of two team members each for project site visits accompanied by project staff.  One group visited Sankuyo, Xai Xai, Kasane, Shororbe and Chobe over a seven day period.  Another visited Twsapong Hills, Mmatshumo, Kubu Island, Gweta, Kuru and Ghanzi over a seven day period.  The third group remained in Gaborone to continue interviews and met the other teams for three days at Maun during which time they interviewed district staff.

Two of the team members left shortly after the field trip, the other four remained in Gaborone conducting follow-up interviews with government and NGO representatives, reviewing documents, and preparing the preliminary draft report and executive summary.  The rest of the team members left after the third week leaving the preparation of the draft final report to the team leader.  The team leader held briefings with the USAID Strategic Objective Team, the Inter-Ministerial Coordination Committee and representatives from NGOs.  Insight and comments obtained from these briefings were included in the Final Draft document which was left with USAID on his departure the 22 November, 1996.

2.0	Strategic overview

2.1	Socio-economic context in Botswana

Botswana is a relatively large, sparsely populated country with a dry climate and large numbers of cattle and wildlife dispersed among the rich, albeit fragile, Kalahari, Chobe and Okavango ecosystems.  Landlocked between South Africa, Namibia, Zambia and Zimbabwe, the country is approximately the size of France and has a human population of 1.3 million.

With just over twice as many head of cattle as people, the country’s natural resource base is under severe pressure. Its magnificent, free-roaming  herds total an estimated 1 million animals and include over 60,000 elephants, the largest concentration on the African continent.

Botswana is a landlocked country, bordered by Zambia, Zimbabwe, Namibia and South Africa, which straddles the Tropic of Capricorn in the center of the Southern African Plateau.  Botswana's is a rapidly growing, young population.  In 1991 it was estimated at 1.3 million, with over half aged less than 15 years.  With a growth rate of nearly 3.5 per cent each year, improved health facilities, declining infant mortality and increased life expectancy, the official population estimates for 2010 are at 2.5 million people.  As Botswana's human population increases, it will clearly need more water, space to live and resources to be employed for subsistence.  Today Botswana's urban areas are growing at a rate of 10% per year, as more and more people come to the cities in search of the employment, water and services which are disappearing in their villages.

Botswana remains, however, sparsely populated.  The majority of the people live in the eastern region of the country, which has a somewhat less harsh climate and more fertile soils than the country's other regions.  The northwestern area of the country contains the Okavango Delta, while the central north-east is a large area of calcrete plains bordering the Makgadikgadi Pans.  The rest of Botswana is covered with the thick sand layers of the Kgalagadi Desert, which accounts for more than two-thirds of the land area.  In most areas of the east there are 30 people per square kilometer, while in places in the Kalahari there are thirty square kilometers to each person.

Botswana's per capita GNP in 1993 was $US1,050.  At independence, livestock, crops, hunting and gathering accounted for about 42% of the country's GDP.  While mining of diamonds, gold, nickel, soda ash and goal bring significant foreign exchange assets, today the agricultural share of the GDP has dwindled to a mere 3%, reflecting a shifting dependence, economically speaking, from renewable to nonrenewable resources.

One contributing factor to the decreasing value of agricultural production in Botswana is drought.  Drought has plagued Botswana for eight of the last ten years, threatening its land, wildlife habitats and ultimately its people.  Drought has forced the national livestock heard down by one third.  Additionally it has put Botswana's magnificent herds of zebras, impalas, giraffes and elephants under increased pressure for survival.  These unique natural resources contribute to attracting almost a million foreign visitors annually who generate almost P200 million in foreign exchange.  It is evident that sustaining Botswana's wildlife populations in the face of environmental crises is crucial to the continued viability of the country's economy.

The people of Botswana are intimately and inextricably linked to the land on which they live.  With approximately three quarters of the population living in rural areas, the livelihood of most Batswana is dependent upon the continued growth and development of the country's natural resources.  When intensive grazing devastates areas around boreholes or when the sources of veld products dwindle due to over consumption, the majority of Batswana must struggle to survive.  People in the rural areas of Botswana can usually find no other employment near home and for most there is no alternative way of life.

2.2	USAID structural re-organization

During the life of this project USAID has undergone internal re-organization.  The Botswana component forms a part of the regionally funded project assistance to SADC.  It is based on a bilateral agreement between the USAID/Botswana Mission (now closed) and the Government of Botswana.  On September 30, 1995 management was transferred to the new Regional Center for Southern Africa, based in

Additionally, USAID is undergoing an internal re-engineering that is intended to increase its effectiveness and responsiveness to development program. Under this new system, strategic objectives are set and a results framework developed that will lead to achievement of one or more of the strategic objectives.  NRMP directly affects strategic objective three, key regional conditions established that support sustainable increases and agriculture/natural resources productivity by small holders, and, as this report discusses, in the strategic objectives to support small and medium enterprises, democracy and governance.  Shaikh (1996) gives a detailed analysis of the strategic objective linkages with the Botswana component of NRMP.

2.3	Botswana Policy and Institutional Environment

During the early 1970s the Government of Botswana came to recognize that the fate of its people and its resources were bound as one.  Thus the government began formulating approaches to striking a balance between human economic development and the conservation of Botswana's natural resources.  The government developed a variety of policies and programs, presented to the public through nationwide consultations, aimed at improving the management of Botswana's range lands.  While the programs did address Botswana's total resource base, they focused primarily on cattle, the lifeblood of the agricultural economy which accounts for three-fourths of the nation's combined livestock and wildlife.  For instance, large scale cattle owners were encouraged to move to "commercial areas" where they could establish fenced ranches in exchange for a rental payment to the District Land Board.  Grazing pressure in the communal areas would be relieved, thus enhancing herd productivity while at the same time providing a more equitable distribution of land for rural people.

In the 1980s and early 1990s, government agencies and development organizations began suggesting that natural resources could provide a sustainable source of employment opportunities and rural income generation in Botswana.  (Republic of Botswana 1986; Ministry of Finance and Development Planning, 1991).  Projects incorporating community-based resource management were initiated in several parts of the country, including Mabutsane in Southern District, Kedia and Nata in Central District and in the Chobe Enclave.  Analyses of these projects indicated that sustainable development could only be achieved if careful attention was paid to the resource base, participation of local people in decision-making, strengthening of resource management institutions, a multi-faceted approach to economic promotion and environmental conservation and education efforts.

The main body of law and regulations that govern resource management include the National Development Plan 7, Wildlife Conservation Policy of 1986, Tourism Policy of 1990, and the Wildlife Conservation and National Parks Act of 1992.

Botswana is in the process of developing its eighth National Development Plan (NDP8) which will move toward encouraging a partnership between the GOB and communities.  NDP 8 will favor communities which demonstrate initiative and commitment to sharing resources.  In order to respond, the GOB will have to coordinate activities of GOB units in several Ministries.  NDP8 will favor private sector initiatives to increase efficiencies “to reduce red tape”.  A role of GOB units would be to facilitate the contacts between the private sector and CBO’s (something like DWNP/NRMP does now).

It is within this context that the Natural Resource Management Project was established in 1989 to apply the concepts of sustainable utilization to natural resources.  The project was designed to promote sustainable, conservation-based development on lands that are marginal for crop production and domestic livestock.

2.4	The Regional Natural Resources Management Project

The SADC Regional Natural Resource Management Program (NRMP) was designed to facilitate regional cooperation through bilateral activities in Zambia, Zimbabwe and Botswana as well as a regional coordination element located in Malawi.  This $44.53 million program will assist community based wildlife utilization projects that promote the conservation and sustainability of the local natural resource base as well as providing economic or nutritional enhancement.  To do this the project will support training, technical assistance, special studies and community pilot demonstration programs. The goal of the project is to improve the social and economic well-being of residents of targeted rural communities by implementing sustainable community based wildlife and other natural resource conservation and utilization programs.

The project, is funded by USAID as part of its assistance to the SADC region which aims to promote sustainable, conservation-based development on lands that are marginal for crop production and domestic livestock.  Its objectives are:

-To demonstrate that sustainable natural resource utilization is a profitable and viable development option for rural communities.

-To increase local employment and incomes through diversifying employment opportunities in the sustainable utilization of natural resources.

-To strengthen local institutional decision making and management units

-To improve the participation and role of women in resource management programmes, thereby improving their incomes.

-To strengthen staff training and career development for employees of the Department of Wildlife and National Parks

2.5	The Botswana Natural Resources Management Project

Outputs of the Botswana NRMP promotes two purposes.  The first is to demonstrate, through practical examples, the technical , social, economic and ecological viability and replicability of community based natural resource management and utilization programs on marginal lands for increasing household and community incomes while sustaining natural resources.  The second is to improve national and local capabilities to ensure the maintenance of the natural resource base through training, education, protection, communication and technology transfer.  The key implementation agency is the Department of Wildlife and National Parks (DWNP

The objectives of the project were to be reached with the support of a six person technical assistance team working with the DWNP, and three technical assistants working with the Botswana Wildlife Training Institute.  The team is supported by a chief of party and an administrator.

The goals, purposes and objectives for the project are as follows:

Goal:		Increase incomes and enhance capability to meet basic human needs through sustainable utilization and conservation of natural resources, particularly wildlife.

Subgoal:	Promote sustainable development of communities on lands that are marginally suitable for agriculture

Purposes:

1.	To demonstrate, through practical examples, the technical, social, economic, and ecological viability and replicability of community-based natural resources management and utilization programs on marginal lands for increasing household and community income while sustaining natural resources.

2.	To improve national and local capability to halt the decline in the wildlife resources base through training, education, protection, communication and technology transfer.

Objectives:

1.	To demonstrate that sustainable natural resources utilization is a profitable and viable development option for rural communities

2.	To increase local employment and incomes through diversifying employment opportunities in the sustainable utilization of natural resources.

3.	To strengthen local institutional decision making and management units so as to empower them to become self-sufficient managers of their local resources.

4.	To improve the participation and role of women in resources management programs, thereby improving their incomes.

5.	To strengthen staff training and career development for employees of the Department of Wildlife and National Parks.

The 1993  mid-term evaluation of the NRMP recommended, inter alia, an additional component to the project to support non-governmental organizations.  This resulted in the formation of the Institutional Reinforcement for Community Empowerment (IRCE) component with the following additional objectives:

1.	Capacity building for non-governmental organizations to empower communities to manage their natural resources in a sustainable manner.

2.	Development of a grants mechanism to support community-based natural resource management/utilization projects.

The NRMP consists of six components to achieve the above seven objectives, aimed at developing the capacity within governmental and non-governmental organizations to facilitate CBNRM:

(A) 	DEMONSTRATION PROJECTS IN COMMUNITY BASED RESOURCE UTILIZATION which are predicated on defining the resource base as a community asset.  Community based projects to be supported will be based on wildlife utilization through tourism, hunting, processing and marketing animal products, and the  sustainable utilization of veld and forest products.

(B)	PLANNING AND APPLIED RESEARCH will support the development of management plans for the northern national parks and reserves, and for the national network of Wildlife Management Areas (WMAs).  The impact of project activities will also be monitored and evaluated under this component.

(C)	ENVIRONMENTAL EDUCATION activities will increase public awareness of environmental issues through curriculum development, teacher training, and non-formal education.

(D)	PERSONNEL PLANNING AND TRAINING to strengthen staff training and career development for employees of the Department of Wildlife and National Parks.

(E)	REGIONAL COMMUNICATION to provide a way to share experiences through exchange visits, workshops, seminars and the establishment of a SADC regional data base.

(F)	CBO/NGO CAPACITY BUILDING to strengthen the organizational capacity of CBOs/NGOs for community based natural resource management

2.6	Mid-term evaluation

The Mid Term Evaluation Confirmed that there were serious design flaws in the project design. It was stressed that the NRMP was hypothesis testing and that several assumptions were incorrect.

1. 	CBNRM had been developed, tested, and was ready for widespread demonstration with support from project funds.

2. 	Wildlife numbers were adequate to permit community subsistence utilization on a sustainable basis.

3. 	That there were sufficient NGO resources within Botswana who were both willing and able to work with communities and the project to mobilize CBNRM initiatives.

4. 	This process could take place within a five- seven year project cycle.

CBNRM had not been tested in Botswana under the existing policy and government structure or within the Botswana cultural context.  Wildlife numbers were not sufficient for subsistence harvesting. Subsistence harvesting did not produce enough returns to cover the equipment and training investment required. Although there were numerous NGOs present they had their own outside the natural resource sector.   There was insufficient NGO capacity to carry out the project’s intentions and the project’s designed intentions were unsustainable and damaging to the wildlife resource. .

Several changes needed to be made in staffing to carry on, as the new hypothesis differed substantially from the original hypothesis

The evaluation made recommendations in two stages; the first being the overarching strategic recommendations. These were seen as what needs to be done. The second set of recommendations were specific recommendations on resources needed to do what needs to be done.

The strategic recommendations were set in three paragraphs as follows.

#	Vigorously continue to strengthen DWNP and provide it with a more tightly focused action-research agenda: implement the NRMP training amendment with dispatch; undertake a coordinated program of systematic hypothesis testing to develop viable integrated conservation and development approaches and methods that will yield demonstration results for extension across Botswana and potentially the region.

#	Undertake a new, expanded project component to strengthen local NGOs so that they participate effectively in the design and implementation of community based natural resource management, thus extending the effect of the NRMP and better assuring the sustainability of it’s results; implement a systematic program of NGO capacity building that will draw on both international and local expertise and will feed back and reinforce project activities over time.

#	Substantially increase the vigorous exchange of information, experience, and lessons learned among all key stakeholders in local communities, government, the NGO community, and regional activities through a program of professionally facilitated workshops, conferences, team-building activities, and non formal education that is grounded in Botswana’s national commitment to consensus-reckoning consultation.

The supporting recommendations falling under these strategies were:

#	Appoint a senior environmental policy analyst to facilitate integration of NRMP activities among key cooperating ministries and to support implementation of the National Conservation Strategy, to be located as deemed by government.

#	Involve a range of stakeholders- including the research division of DWNP, local community designates, representatives from the tourist industry, and researchers from the Ministry of Agriculture- in the assessment of Botswana’s natural resource base in order to improve the quality of baseline information, to establish sustainable levels of resource utilization for both wildlife and vegetative resources, and to build planning consensus among interested parties.

#	Make a clear separation between community mobilization and development initiatives and the process of socioeconomic monitoring and evaluation; appoint two senior advisors, one to each of these efforts, who are charged with developing prototype activities and strengthening institutional capacity within DWNP.

#	Work with communities to protect their resource base through collaborative enforcement and to promote a major attitudinal switch from previous interactions between DWNP and local communities.

#	Continue and accelerate the implementation of participatory rural appraisal methods as a key tool for extension and community mobilization. As the indicator of NRMP’s commitment to the use and application of participatory rural appraisal methods, it is recommended that by PACD at least 50% of subproject activities in implementation or the planning phase should have been developed through such methods.

Now with the benefit of 20-20 hind site, it is obvious that if a senior policy advisor had been appointed, it would have taken the full term of the appointment to become familiarized and build up the trust necessary to begin functioning. It was much more efficient to assign this function to the COP these policy tasks which he had already commenced, and proceed with the policy work without the long break in period a new assignee would require.

Involving a large diffuse group in the specific task of determining the extent of the natural resource base of the country would dilute and diffuse the core efforts of the project and should not have been a recommendation from the mid-term.  The one  member of that team that is on this team can’t recall this even being discussed with him.

All of the other recommendations have received action and the results have been quite positive, exceeding expectations in most cases as outlined in this report

2.7	Other donor involvement

USAID and the Government of Botswana are the major contributors to the NRMP.  Other donors provide substantial direct or indirect support to activities that complements the project. The other donors providing support include:

European Community (EC).   The EC has two separate projects working in DWNP under it’s Wildlife Conservation and Utilization in Botswana Project - one dealing with the four northern parks/game reserves (Chobe, Moremi, Nxai/Makgadikgadi) and the other with the 3 southern parks/game reserves (Gemsbok, Central Kalahari and Kutse).  These projects focus improving protected area management and tourism development through  improving upon and implementing management plans, infrastructure development.

Overseas Development Authority (ODA) - ODA supports the DWNP institutional strengthening of the DWNP, strategic plans, mission statements.  Their first phase of assistance ends this December which developed mission statement, TORs and code of conduct.  Depending on government progress towards reform, they will support institutional reform process for next phase, including devolving authority to the districts.

Netherlands Development Program (SNV).  Inspired by NRMP activities, SNV is increasing becoming more involved in community based natural resource management because of NRMP  They are supporting 4 initiatives in the country based on wildlife and veld product utilization and support a technical advisor at Veld Product Research.

Global Environment Facility/IUCN (GEF).  Since 1993 GEF has been supporting community based initiatives.  It currently supports a total of 15 projects nation wide, six  of which are CBNRM.

Royal Norwegian Embassy.   Supports GEF and IUCN in their capacity building projects and .  Provides support to Kuru Development Trust.  Most of their focus is on institution cooperation, linking with Norwegian institutions.

Norwegian Agency for International Development (NORAD).  NORAD has been active in supporting Permaculture to work with Basarwa communities and addressing rural poverty. Supports the Remote Area Dwellers Programme, which is a major mechanism for government to address development issues in remote area dwellers settlements. Collaborative support with IRCE has led to several initiatives in NGO capacity building with the aim of strengthening national NGO advocacy for empowerment in Botswana’s civil society.

Swedish International Development Agency (SIDA).  Support to environmental education activities at the University of Botswana.

Japanese International Cooperation Agency (JICA).  Provided video van for the Television Trust for the Environment (TVE) component of the environmental education activities of NRMP.

International Fund for Agriculture Development (IFAD).  Signed protocol with the MFDP in 1995 that will support 25,000 to 50,000 people through community based natural resource management.  Supported several studies including Geoffrey Tylers report on The Contribution of Community-Based Wildlife Tourism to Botswana.

3.0	Response of implementing agencies: a review of project activities and components

3.1	Policy development and institutional capacity-building

3.1.1	Background

The policy component of the project is part of the package of activity recommended in the mid-term evaluation.  Although the project had been assisting on departmental policy before this by drafting of guidelines for community activities and the guidelines for joint ventures, no formal project component was designed for policy development.

Although not a specific component addressed in all project papers,  NRMP’s institutional capacity-building functions is inherent in all of its activities.  This section is included in the report to highlight some of the accomplishments of the project and to point out some of the opportunities available for Government and the Project to increase the effectiveness of institutions for community-based natural resource management.

Given the nature of the project, building institutional capacity of communities to manage their natural resources has been the main focus. In this context, the project has undertaken activities for building technical and organizational capacity of communities and supported policy initiatives to institutionalize community-based natural resource management.    The extent of this capacity-building at the community levels is dealt with in more detail in section 3.3   NGO capacity-building is addressed in this report in section 3.4.

3.1.2	Key elements and progress to date

Policy

Two major activities have occurred within the past year:

The NGO Task Force for Conservation in Botswana is a grouping of NGOs that have come together to support efforts to reverse declines in the nation’s wildlife and to help achieve greater recognition of the role that wildlife can play in the national life of Botswana. As a result of a meeting attended by NGOs, Private sector and government representatives, a group of NGOs created a task force to bring these concerns to the attention of the President of Botswana.

The NRMP was asked to fund two consultants to report technically and legally the options recommended for reversing the wildlife decline.  The report was presented and the NGO task force presently awaits the response from the office of the President.

Community utilization policy review.  The main body of law and regulations that govern resource management include the National Development Plan 7, Wildlife Conservation Policy of 1986, Tourism Policy of 1990, and the Wildlife Conservation and National Parks Act of 1992.  These documents state various aspects of the government’s desire to decentralize the management of natural resources, diversify the rural economy and improve the participation of Batswana in the tourism and wildlife utilization industry.

However, the existing laws and policies tend to contain overall intent but no guidance on the application of these policies.  The NRMP is presently assisting the DWNP to review and consolidate existing procedures into a coherent community-based natural resource management policy statement.  Once vetted within the department, the new policy will be submitted to government for review and approval.

Conclusions

While Botswana has a substantial policy framework in place for the management of natural resources,  there are policy areas that need additional attention.  Most of these center on strengthening the national policy framework to govern community-based natural resource management.  Two key policy areas that need additional work to strengthen the sustainability of community-based natural resource management are as follows:

-Development of a legal and regulatory structure that defines veld resources as common property rather than open access resources, that can be managed by representative and accountable CBOs.  The project in its role as promoter of veld products utilization for community benefit, can play a central role in this policy development.

-Regulations to guide the exercise of authority within Wildlife Management.  In the absence of regulations, contravention in gazetted WMAs go unchallenged.  Several WMAs, particularly those in Kgaligadi District are not gazetted and are lacking implementation of the management plans. The development of WMA regulations require wide consultation within government and the resident populations.  In order for community-based natural resource management to be sustainable in these areas,  the Project should emphasize the operationalization of Wildlife Management Areas and their management plans and support to establishing effective regulations.

Application of existing policies needs to be strengthened across sectors, so government department are working towards a common goal.  An example of policy implementation is seen in the instructions to local officials issued jointly by the Ministry of Commerce and Industry and the Ministry of Local Government, Lands, and Housing, stating, among several other important community management policies,  that the Joint Venture Guidelines are binding on all districts.  While the application of existent policy at the action level is now being addressed by the project, this still remains one of the major aspects of the policy job remaining

More resources are needed at the district and sub-district level for policy knowledge and awareness building such as set of district institutional guidelines.  As more application of policy takes place,  the needs will become apparent and can be addressed at that time.  Additional guidelines such as trust formation, benefits distribution, or accountability may be needed.

A new opportunity for wider policy dialogue is the new Botswana Institute for Development Policy Analysis (BIDPA), a think tank/consultancy firm with a strong, powerful board made up of representatives from the Bank of Botswana, Ministry of Finance and Development Planning, parastatals and private sector representatives. They are exploring how to help the government to get away from a mineral-based economy towards manufacturing, tourism and agriculture.   The project should make regular contact with BIDPA in view of providing information on new tourism developments and wildlife utilization.  On the other hand, BIDPA has macro-economic information that will benefit the project.

Implementation Issues

Policies supporting community-based natural resource management are, by nature, multi-sectoral and therefore policy formulation needs to have wide consultations among the appropriate sectors.  This should be recognized as a necessary, time consuming process.  In particular, increased dialogue with, and engagement of the Ministry of Agriculture, specifically the Range Ecology Section and the Agricultural Resource Board,  needs to be improved.

Recommendations:

1.	The Chief of Party position should continue for two additional years.  Part of the COPs terms of reference should include assisting DWNP to formulate CBNRM policies.

2.	The project should continue to assist in policy development where possible.  Examples of future policy work that may be needed include regulations for WMA management and cooperative management between parks and people.

3.	As conditions warrant, the project should direct increasing attention to consideration of the open access question of veld resources.  This should be done to the extent of where this differs from the solutions being promoted for wildlife.

4.	Assist DWNP and other policy stakeholders to complete the process of consensus building, amendment, adoption and implementation of the community-based natural resource management policy document currently under preparation.

Institutional Development

National level

The formation of the Community Extension Unit of DWNP under the NRMP has been instrumental in developing and changing the function and mission of the DWNP.  In the past relations between the DWNP and people were extremely poor, as the department had a mainly law enforcement function.  With the advent of the extension unit and a focus on community development this role is changing.  As opposed to being seen as only policemen, DWNP personnel are beginning to be seen as partners in the development of community-based enterprises and in controlling problem animals.

A new opportunity to promote better relationships with tour/safari companies and the districts or communities is with the Hotel and Tourism Association of Botswana (HATAB). Tour operators that operate without any standards raise two fears: 1) they may unfairly influence communities, 2) despoil tourist. HATAB has 120 member companies but at the moment are not licensed, nor are references checked to see if they are in good standing.   Government has created conditions for private sector involvement, but no conditions have been set on how the tour companies deal with the communities.  HATAB has the interest to become more involved in the regulatory part of the private sector and sees community tourism as a potential area.  There is a need to help commonties negotiate terms with government for standards of tour operators which HATAB could oversee, and NRMP assist in.

District level

Districts provide the most promising entry point towards ensuring institutional capacity to further community-based natural resource management.  However, much work remains in capacity-building and strengthening links between national level institutions, districts and the communities.  There is an opportunity to assist building representational, accountable civil society by linking planning and implementation activities within the Village Trust Committee  through the VDC and the district development planning process.  Already, the Mababe community is poised to engage the VDC as the main vehicle for community-based natural resource management.

The proposed Community-based Programme Strategy of the Rural Development Division of the Ministry of Finance and Development Planning  is intended to contribute directly to the challenge of expanding rural economic activities and reducing poverty.  The major objective will be to assist people living in rural communities to improve their livelihoods and to reduce poverty.  A further objective will be to introduce a more effective and sustainable approach to rural development by substantially increasing the role of community participation and community leadership structures.  The RDD is not an implementing department but other agencies for on information from which they develop guidelines and directions for rural development.  NRMP provided information on their experiences with establishing trust to the RDD which allowed NRMP experiences to be incorporated into their work thus moving a sectoral development onto the national stage.

The community-based programme strategy includes, inter alia, the transfer of decision making responsibility and control to communities, community action plans for increasing incomes and employment, and experimentation and refinement of approaches during an initial three year pilot phase.

The support activities to CBOs require that district units exercise coordination. Inter-departmental coordination tends to be easier at the district level.  A district official spoke of four legs of a cow that must work together if objective is to be achieved.  The four major pillars at the district level are 1) District Administration as coordinating unit; 2) Land Board in dealing with Tribal Lands; 3) Tribal Administration;  and 4) District Council (District Development Committee).  The NRMP has played a role in helping these units work together.  Training and capacity-building activities undertaken with communities often include active, direct involvement with relevant district officials in problem solving, decision making and leadership development.

DLUPU appears to be a viable Governmental institution at the district level for integrating community activities since it brings all relevant departments together.  However, integration will not happen where DLUPUs are weak or where policies have not yet been defined, or decentralized, by the home ministries. A case in point is the Kavimba (CHOBE) proposal to extract dead timber from the forest reserve.  While the regional forestry officers have developed guidelines to facilitate such a project and have petitioned their Ministry to change the currently policy which prohibits any development from taking place within the reserves, they are awaiting action by HQ.

Problem animal control is the first and most contentious point of contact between the rural public and wildlife and therefore is a major extension issue.  In this context, the formation of the Problem Animal Control (PAC) Unit set a precedent for DWNP.  The PAC Unit (formed in 1993, it has a total of 39 officers trained) selected people by standards set by the Department.  DWNP lacked trained staff to deal with problem animals and their inability to respond led to bad relations with villages.  District Officers are requesting more officers than have been trained.   This has been much appreciated by the districts and remains one of their primary concerns.

Village, Community-based Organization Level

As stated, this is dealt in more detail in section 3.3 and 3.4.  However, it should be emphasized that the goal of policy and institutional development at national and district level is in the context of providing support and services at the community level.  More importantly, this includes establishing an enabling environment that allows communities to develop and thrive, with less dependance on government subsidies.

Implementation Issues

NRMP and DWNP has had considerable success in building institutional capacity for CBNRM considering many constraints facing it.  A major constraint is the weakness of the DWNP who has the responsibility, but little authority over the human, financial and material resources under its command. This is manifested by the sporadic presence of counterparts from DWNP over the life of the project.

The Community Extension Unit is still weak in numbers and can not respond to all the requests being made.  As an example,  non-extension people are frequently called upon to respond to community requests.  Another indicator is the high demand for Problem Animal Control officers who must deal with the demand by the communities to deal with problem animals.

Moreover, there is not yet a critical mass of government staff at the district level in the District Land Use Planning Unit  which includes forestry, crop production, livestock, wildlife, lands, local government, Agriculture Resource Board and the Land Board who both understand and support CBNRM to provide the initial advice and support necessary for replication throughout Botswana.

Recommendations:

1.	To maximize support to the DWNP the department should permanently assign counterparts to NRMP advisors instead of sporadically.   This must include the required resources necessary for the counterparts to work effectively. More than one counterpart for the advisors would be most beneficial. Moreover, input from NRMP on which counterparts are selected would be beneficial to ensure that the individuals have the appropriate skills and aptitude for the work.

2.	District Administrations should also appoint counterparts officially to project staff  to maximize transfer of skills.

3.	The project should focus more on building capacity of the districts to assist communities in natural resource management  and to incorporate community action plans in the district development plan.  An obvious entry point is to work with a district/community team to formulate and implement community action plans.  This will ensure inclusion of action plans into the district development planning process.   All counterparts should be engaged in this process where possible.  IRCE should provide support to ensure that this link between communities, district and national government is effective and responsive.

4.	NRMP should assist HATAB to explore possibilities for defining and implementing standards for tour operators vis a vis the communities.

3.2	Planning and Research

3.2.1	Background

This component of the project includes two major outcomes: development of protected area management plans and the establishment of a monitoring and evaluation system.  Deliverables for the components included:

-Management plans for four protected areas and 12 Wildlife Management Areas are drafted and approved by relevant District Land Use Planning Units

-At least two case studies illustrate the utility of land use planning in Botswana.  Cases will be chosen from the natural resource land-use category.

-At least two socio-economic studies compare baseline and follow-up data from the selected sites for the demonstration projects, and drawing conclusions on the impact of the wildlife utilization program on residents.

-Project funds will support studies exploring the international markets for wildlife products.

-Policy support being provided to the Ministry of Commerce and Industry.

3.2.2	Key elements and progress to date

National Park and Wildlife Management Area Management Plans:

The project originally called for management plans to be produced for the four northern national parks/game reserves (Chobe, Moremi, Makgadikgadi, Nxai Pans) and for twelve Wildlife Management Areas (Groote Laagte, Maitlo-a- Phuduhudu, Okwa, Kgalagadi, Southern, Kweneng, Kwando, Okovango, Nunga and Nata, Boteti and Ngamiland State Lands.  Ten management plans have been completed by the NRMP, four other plans will be completed within safari concession areas by the tenderers and the remaining two area plans have not been requested by the district.

Table X: Status of Protected Area Management Plans

| Protected Area | Contractor | Comments |
| --- | --- | --- |
| Makgadikgadi N.P. | IUCN | Completed. Includes Nxai pan, two areas amalgamated into single Park |
| Nxai Pans N.P | IUCN | Completed |
| Moremi N.P | KCS | Completed |
| Chobe N.P | KCS | Completed |
| Groote Laagte WMA | RPM | Completed |
| Maitlo-a-Phuduhudu WMA | RPM | Completed |
| Okwa WMA | Mark Murray | Produced by independent consultant with DC funding |
| Kgalagadi WMA | Natural Resource Services | Completed |
| Southern WMA | N/A | MP not yet requested by District |
| Kweneng WMA | N/A | MP not yet requested by District |
| Ngamiland State Lands | N/A | Safari concession area. MP to be produced by tenderer |
| Kwando WMA | Okavango Community consultants | Completed |
| Okavango | Okavango Community consultants | Completed |
| Nata State Lands | N/A | Safari concession area. MP to be produced by tenderer |
| Nunga | N/A | Safari concession area. MP to be produced by tenderer |
| Boteti State Lands | N/A | Safari concession area. MP to be produced by tenderer |

Conclusions

The number of management plans to be completed in the short-life span of the project was enormous and could only be accomplished, as NRMP/DWNP did,  by contracting them out to qualified firms.  Development of management plans provided a good opportunity for building the capacity of the implementing agency to identify management problems and options for their solution.

Legislation establishing WMAs was fundamental in enabling NRMP to begin management plan development as it established the legal and institutional framework for action.  Further, though the WMA Act clearly place broad authority for WMA management to the Ministry of Commerce and Industry, no body of regulations has been developed to guide the exercise of authority.  The DWNP has created the post of Wildlife Planning Officer to oversee the implementation of the WMA plans and to work on related land use issues affecting the wildlife resource.   In order for CBNRM activities in these areas be politically sustainable, NRMP should emphasize the operationalization of WMAs and WMA plans through follow-on to the plans and support to establishing effective regulations.

Through the contracting mechanism the project ensured a community component and assessment in the plans.  The quality of this work varies among the different plans. It is generally recognized by other partners and donors within DWNP that NRMP has developed skills and experiences that are of high value for the continued development of these plans.  Because of its workload, NRMP has not been in the position to offer substantial support for requests of assistance on community issues - particularly the Central Kalahari Game Reserve.   The opportunity for the team to have this type of input is advantageous to broaden the scope of CBNRM within the department, particularly in areas that will assist communities to make a stronger link between resource use and conservation activities.  The EC parks project wishes “they could use their expertise if they move into new areas”.  This is another example of the influence the project has had on other institutions.

The management planning activity has suffered from a lack of clear links between the planning and implementation components because of the time lag between management plan development by NRMP and implementation by the Northern Parks Project.  This has increased the workload of the Northern Parks Project as it has to adapt plans that were developed without adequate knowledge of the implementation constraints.

Recommendations

1.	The project should assist in developing management plans for the Kweneng and Southern Wildlife Management Areas if requested by the district, and if the plans can be started a year before the project completion date.

2.	Without prejudice to the projects main community empowerment focus - or it’s efforts towards obtaining unstoppable momentum for CBNRM the team should assist DWNP in incorporating community issues in management plan adaptations and implementation activities

Community Action Plans and Participatory Rural Appraisal

The project has initiated the use of participatory rural appraisal (PRA) to develop community action plans at the village level.  In 1994 PRA’s were conducted in three of the five Chobe communities.  These led to Community Action Plans which are being facilitated by CAP facilitators selected by village residents.  Within CECT, the Program Officer is actively monitoring progress by the VTC against objectives of the community action plan.  The remaining two Chobe villages have also requested assistance in carrying out PRAs.  An example of the impact of the PRA process was during the follow-up baseline in Chobe (Ecosurv, 1995) it was found that the knowledge of CECT by villagers was higher where PRAs had been conducted.

Following on the 1994 PRA experience in Chobe,  NRMP community development modified the format employed so that, while participatory assessment is broad-ranging, most planning activities focus on natural resources management and institutional strengthening.

This participatory assessment and planning approach was piloted in Sankuyo and from the outset in 1995, became the vehicle by which Sankuyo residents organized and managed their activities.  The outcomes of these participating activities were detailed natural resource management plans and a community action plan, which lead to the formation of Sankuyo Tshwaragano Management Trust, acquisition of resource management rights and a successful lease/employment relationship which has formed the basis of benefits to the community.  The community action plan also defined a training program intended to provide village residents with skills to manage their area and its resources effectively.

Thus far 12 officers of the DWNP have been formally trained in PRA facilitation.  Additionally in 1996, four CBO representatives (3 from Sankuyo, 1 Chobe) were sponsored for PRA facilitation training at Egerton University in Kenya.  It is hoped that CBO facilitators will be able to team up with DWNP staff to provide facilitation for new participatory planning activities in villages moving towards CBNRM.

A major two-year study has just been completed, commissioned by the Ministry of Finance to determine if PRA, introduced in Botswana by NRMP, can and should be adopted by government as a means of providing extension and a vehicle for incorporating village level input within the District and National development planning process. The primary recommendation of the research, carried out  through the Department of Adult Education and the Department of Social Work  University of Botswana, is “that the Ministry of Finance and Development Planning decide in principle to integrate PRA into the current consultation procedures and practice of coordinated extension activities.”

The three PRAs undertaken in Chobe Enclave in 1994 played a key role in this finding.  Kavimba, Kachikau and Parakarungu were comparatively evaluated alongside six other sites.  The Chobe PRAs are determined in the report to be far and away the most successful among the nine sites considered in terms of progress in implementation of the community action plans. The report states that “the PRAs done by NRMP-DWNP in Chobe led to a progress score which is much higher” than the others (“a remarkable 90%, 74% and 71%” of tasks being implemented). The success of the Chobe model is attributed to its unique program for facilitating community-driven implementation involving a community-selected stipended volunteer as a  “Community Action Plan Coordinator.”  This model is to serve as the basis for recommended Ministry of Finance attempts to replicate  the success of the NRMP-DWNP approach.  This finding, if implemented by government, can have major impacts for democracy and governance issues by decentralizing development planning and placing initiative more squarely in the hands of rural residents.

In addition, with support form NRMP, the Botswana Orientation Centre has created a Participatory Planning and Training Unit, which has carried out numerous participatory rural appraisals.  Ensuring ongoing facilitation after the initial PRA activities is the major need for ensuring both sufficient institutional development and progress in implementation and evolution of CAPs that are created. The project has worked actively to promote BOC as the national secretariat for participatory planning through the national committee chaired by the Ministry of Finance and Development Planning.  IRCE has provided support, through the sub-grant programme and technical assistance for the development of a Community Mobilization Manual and a quarterly newsletter promoting dialogue on participatory planning and mobilization techniques.  This support, coupled with related organizational development interventions, position BOC for an expanded role in participatory planning throughout the country.

Broad Impact

NRMPs participatory rural appraisal efforts and their support to Community Action Plan Coordinators has had a broad impact on governments efforts to base development planning at the grassroots level.  The MFDP report on its PRA pilot projects (1996) states “although PRA appears to be empowering in itself, the presence of follow-up through a CAP coordinator and support from national level doubles the extent to which individuals make claims on village based extension workers and triples the extent to which village based organizations make claims.

Conclusions

PRA’s , however, should not be an end in themselves, but should be promoted only to the extent that they serve as a useful vehicle for managing community driven development.  The question becomes “how are these approaches being used” and “how effective are they on mobilizing and organizing village level planning and action.” NRMP should continue liaising with RDD and BOC to advise on strengthening the governments use of the PRA methodology.

While DWNP and project staff have a long-term vision of the benefits of CBNRM and potential uses of profits, the communities themselves must develop a vision.  In this context, the project should assist the community to develop a vision of where their community would be in the future - 20 or more years.  This vision will help them work towards a common goal and provide insight on priorities for investment of trust funds.

Implementation Issues

Major turnover of personnel in BOC has left that institutions facilitation capacity at a very low level currently.  BOCs unit manager left some six months earlier, replaced by another competent facilitator who left BOC after four months.  The position has recently been filled by a new unit manager with no training in participatory approaches.  The unit currently has 1 junior staff person with PRA training and experience

Another key constraint to the more widely spread use of participatory approaches is that while some 16 DWNP and CBO personnel have been trained in participatory techniques, of these, only one has a sufficiently strong grasp on the issues underlying participatory assessment and planning to play an effective role as trainer/coordinator for participatory appraisals.  This officer returned from two years training in the US in September and is currently on a back to duty orientation tour.

Recommendations

1.	Continue the sociologist position for two additional years to strengthen the PRA process and liaise with RDD and BOC on PRA issues.

2.	Continue strengthening of DWNP and district capacity in participatory planning techniques.

Monitoring and Evaluation - Socioeconomic Studies

NRMP has defined and implemented a framework for monitoring and evaluating CBNRM activities. This framework departs from the premise that CBNRM seeks to change the terms and conditions of resource access in ways that create incentives for people to use resources in conserving and sustainable ways.  The effects of these changes can be seen most clearly in the division of labor that organizes the productive activities in which people utilize resources based on their access to them. At its most basic level, the division of labor organizes production along three axes; gender, ethnicity, and social class. As the terms and conditions of resource access change, this is reflected along the three basic axes of the division of labor, and one can the costs and benefits of these changes for different segments of a population. These costs and benefits are the basis for the incentives that people have to use resources in particular ways.

The monitoring and evaluation system is intended to be used as a planning tool by decision-makers in DWNP and other GOB agencies with an interest in CBNRM, to help them understand the factors responsible for the success or failure of different experiences, so the successful experiences can be replicated and repetitions of the unsuccessful ones can be avoided. To this end, BNRMP’s system meets several critical conditions for a sustainable approach to monitoring CBNRM, by:

1.	Defining the specific kinds of socioeconomic data that are required to know if CBNRM is creating conditions consistent with sustainable resource use;

2.	Permitting meaningful comparisons to be made between CBNRM settings characterized by diverse biophysical and socioeconomic situations; and

3	Allowing the use of a wide range of data collection techniques, based on an institution’s technical capacity and the resources available.

The monitoring and evaluation framework implemented by NRMP draws upon a substantial body of literature  analyzing the socioeconomic processes that shape how people use natural resources. It also incorporates two important components that were in place by early 1995:

1.	Survey data collected by SIAPAC, under the original socioeconomic baseline study conducted in the Chobe Enclave , in 1991, at the outset of CBNRM implementation efforts there; and

2.	Data collected through PRA exercises in the Chobe Enclave villages of Kavimba, Parakarungu, and Satau, which were a central element in the participatory planning exercises to build a consensus about how best to utilize the wildlife resource for the benefit of the local population.

Since the elaboration of an explicit monitoring and evaluation framework, it has guided several specific data collection exercises during 1995 and 1996. These include:

1.	Three socioeconomic surveys conducted to establish a baseline or assess the progress of CBNRM efforts. These include (a) an initial baseline in the Northern Kgalagadi subdistrict settlement of Zutshwa, in support of a CBNRM effort being implemented by SNV; (b) the follow-up to the baseline study conducted in the five Chobe Enclave villages by SIAPAC; and © and an assessment of the progress of the cochineal project being implemented in eight areas of Ghanzi district by Kuru Development Trust, with NRMP support.

2.	A socioeconomic study based on participatory data collection techniques (as opposed to a survey), in the Ngamiland village of Sankuyo, which was part of DWNP/BNRMP efforts to prepare the village to assume responsibility for managing its wildlife quota; and

3.	A topical study of the issues that will affect CBNRM implementation as a result of the need for DWNP to incorporate animals currently hunted under Special Game Licenses into the hunting quota system.

In addition, the project links data from the monitoring and evaluation system into AID to monitor people level impacts of the project.

Conclusions

The M&E component provides a good mechanism for understanding the social and economic processes that shape how people use natural resources. The information being collected can be used as a planning tool by DWNP, other organizations and agencies with CBNRM implementation responsibilities, and the CBOs themselves. The information being collected by NRMP’s monitoring and evaluation component also will permit testing and refining basic assumptions and hypotheses of CBNRM.

The DWNP sociologist responsible for monitoring and evaluation has made excellent progress in understanding the conceptual basis of CBNRM and the monitoring and evaluation framework. She has also demonstrated her ability to draw on a  range of data collection techniques that provide the information on which the framework rests, and she is assuming increasing responsibility for managing the M&E system. However, she is only one person, and she is a relatively junior officer in the DWNP organization. Therefore, DWNP does not yet have the capacity to respond to the need for socioeconomic data collection and analysis that will accompany the snowballing of CBNRM projects throughout Botswana. Furthermore, there is no one in DWNP’s sociology office with the seniority needed to work with senior management to educate them about how they can and should use the information collected through the M&E system as a planning and management tool.

If she continues to develop her skills and understanding as she has over the past 18 months, the DWNP sociologist will be able to assume full responsibility for managing the monitoring and evaluation system within two years. However, the sustainability of the system within DWNP and its continuing utility as a planning and management tool to support national implementation of CBNRM will depend on DWNP adequately staffing its sociology office, and doing so soon enough to permit the people hired to acquire necessary skills and understanding before NRMP departs.

The monitoring and evaluation component of NRMP has been primarily concerned with establishing a system that provides the information that implementing agencies and CBOs participating in CBNRM need to understand the impacts their efforts are having. This information feeds into the information requirements of USAID, but does not match those requirements exactly. BNRMP has participated in several exercises to satisfy USAID’s information requirements. These include:

1.	NRMP worked with William Fiebig, who was brought to Botswana by USAID with support of the DESFIL project, to plug information about the project into a “results framework” structure that would allow the project to be assessed in terms of its contributions to strategic objective three, and the other strategic objectives of the RCSA.

2.	NRMP participated actively in a regional exercise conducted by the Project Coordinating Committee (PCC) to define an M&E framework for all of the NRMPs in Southern Africa. This included drawing on NRMP’s M&E framework to help organize the conceptual basis for such a framework, and sharing its experience in working with Fiebig to organize project information into a results framework responding to strategic objective three and the other strategic objectives.

3.	DWNP and NRMP will begin working with a USAID-sponsored effort by SACCAR to elaborate a methodology for assessing the economic costs and benefits of CBNRM in the area of wildlife management. The effort will involve BNRMP’s M&E advisor and DWNP officers from the Planning Unit, and will be based on the data collected in the studies BNRMP has conducted in the Chobe Enclave and Sankuyo.

While emphasizing the importance it places on receiving information for its own reporting purposes, USAID has been inconsistent in communicating what information it requires, or in what format it wants to receive that information. The plethora of exercises in which NRMP has participated to provide USAID with information, which depart from overlapping, but different sets of priorities and questions, make it difficult to be as responsive as the richness of NRMP’s information about its efforts might otherwise permit.

USAID’s requirements reflect its need to assess its progress in meeting its strategic objectives, which are based on different premises and cause USAID to ask different questions than do DWNP, NRMP, and organizations with CBNRM implementation responsibilities. NRMP has and will continue to provide USAID with the information it needs to fulfill its reporting requirements. This relationship could be improved if USAID communicated its information needs more clearly and consistently.

Recommendations:

1.	The monitoring and evaluation position should remain for an additional two years.

2.  	Further socio-economic surveys should be conducted as required both to establish baselines in new project sites and to judge impacts over time.

3.	USAID, in concert with project staff, needs to clarify data required to report on its project indicators, including interval for reporting.  These indicators must more closely correspond to actual project activities.

4.	Benefits analysis and/or changes in access and control of resources should be done on a regular basis to mitigate unforeseen negative impacts of project activities.

3.3	Community-based resources utilization: demonstration projects

3.3.1	Background

Demonstration projects supported by NRMP fall under three main categories of resource utilization: consumptive use of wildlife and veld products, and; non-consumptive (mostly photographic tourism).  With the exception of Khwai, all the current community-based consumptive wildlife projects are earning part of their income from photographic tourism.  At the present time this is a small proportion of the income derived.  Through IRCE the project has provided capacity-building support to ensure broad based benefits, transparency and sustainability of activities.

3.3.2	Key elements and progress to date

Thirteen different community-based resources utilization activities are underway at the moment.  These thirteen areas affect over 50 separate villages or settlements and assisting in the range of  50,000 people. At the beginning of the project, activities for community-based resource utilization was mostly  focused on wildlife utilization.  The project is now also working more actively on assisting communities to harvest and market veld resources which are potentially lucrative.   Table x gives a summary of current activities, a more detailed summary is found in annex 3.

Table X: Summary of Community-based Resource Utilization Activities

| Location | CBO | Partner Organizations | Use | Status |
| --- | --- | --- | --- | --- |
| Chobe Enclave | CECT | N/A | Wildlife Quota | on-going, IRCE conducting organization capacity building and training, Community Escort Guide training continuing, presence of a CDA. |
| Ngamiland | Sankuyo Tshwaragano Management Trust | NACOBTA/ NAMIBIA | Wildlife Quota, Photographic Tourism | on-going, escort guide training and NRM advise, institutional capacity-building, IRCE training |
| Ngamiland | Okavango Community Trust | N/A | Wildlife Quota Photographic Tourism | on-going, responding to request for support |
| Ngamiland | Khwai Village Trust | University of Botswana/GEF | Wildlife Quota for direct consumption | on-going, NRM plan and CAP completed, advice as requested |
| Ngamiland (west) | !Kokono Crafts Quota Management Committee | SNV | Wildlife Quota for direct consumption Photographic Tourism Ostrich Eggs | on-going, run by SNV with input from NRMP on NRM. |
| Kgalagadi (Ukwi and Zutswa | None registered | SNV, Thusano Lefansteng, Maiteko Tshwaragano Development Trust | Wildlife Quota Veld products | District interest in CBNRM |
| Ghanzi | None registered | N/A | to be determined | District approved utilization as development tool. Okwa WMA chosen after exchange with peers Chobe. NRMP will support DWNP extension officer. Advise on NRM use options |
| Mababe | None registered | N/A | to be determined | committee being formed, NRMP responds to request. |
| Kgalagadi (Ukwi & Zutswa | None registered | SNV Thusano Lefatsheng | Wildlife Quota Veld Products Grapple, teas | opposition from cattle interest demonstration plots established |

| Location | CBO | Partner Organizations | Use | Status |
| --- | --- | --- | --- | --- |
| Ghanzi | KDT | Unilever (potential buyer) | Cochineal Veld foods | Start-up grant provided, plots in 8 settlements |
| Ghanzi, Kgalagadi | Craft Marketing Organizations | Klein Karoo Cooperative (supplier and potential buyer) | Ostrich Eggs | whole ostrich eggs distributed, links to supplier made |
| Tswapong Hills | Local groups, women | KCS, WFH | tourism (KCS) Phane worms (KCS, WFH) | start-up phase |
| Gweta | Gweta Trust | Number of potential buyers and Joint Venture partners | Bottled Water Tourism Camp Marula fruit | market test site selected first year trials conducted |

Conclusions:

The original project design and the mid-term evaluation called for two of wildlife utilization activities and four veld product activities.  At present there are no resource utilization activities or Trusts that would run on their own.  Of the five Trusts visited by the evaluation team, each is at a critical stage in their genesis to becoming viable Trusts that will manage enterprises, negotiate with other parties, and follow procedures either established by themselves or stipulated by law.  Only when they reach this point will they be in a position to make collective decisions aimed at improving their livelihoods and reduce degradation.  And it is at this point that they will become models for other communities in Botswana and in the sub-region.

The time period stipulated in the original design for establishing viable Trusts has proven to be too short.  At the time of the original design, neither USAID nor other partners had sufficient experience to assess the time required for establishing viable CBO’s.  Because of the NRMP experience in Botswana and experiences elsewhere, we can say something more about the obstacles that are required before viable models are produced.  First, perceptual changes have to occur among a number of groups.  Up to now, the State has been the main benefactor in providing communities with essentials.  There has not been a reason for communities to organize to deal with questions of prioritizing objectives and of mobilizing local resources.  For example, many communities we visited had very good water systems and schools that came from the GOB.  While this largess has been a benefit, it also means that dependency on the State is quite high, and it has not encouraged communities to go through a process of setting priorities and mobilizing local resources for resolving constraints.  But, the capacity for the State to provide essentials is reaching a limit and, under NDP8, the GOB will be moving toward a partnership relationship which will favor communities which show initiative.

A second reason that it has taken time for viable CBO’s to form is the rhythm of the decision-making process at the community level.  The NRMP team has been sensitive of this rhythm and has respected it.  The NRMP shows us that a viable CBO is not formed in isolation of the overall dynamic of community life.  To force a community to commit to an organization at a schedule dictated by a log frame may have produced the development of an artificial organization in which the community may have let the advisors write the constitution and set the agendas.  The advisors did just the opposite.  For example, in Chobe, only three of five villages were ready to conduct PRA’s in 1994.  Instead of forcing the issue (perhaps driven by project targets), the technical assistance went along with the decision and conducted the PRA in only three villages.  Other advisors were asked to explain the CBO principles to Khwai and Mababe which they did.  But, when the advisors found that these communities had to work through other problems, they did not force the issue.  Both communities recently requested assistance from DWNP/NRMP but are unable to follow up because of the pending project completion date.

A third reason—linked to the first two—is a change in confidence in the concept.  We were told several times that the perceptual change was produced at the community-level when the first check was put into the bank.  In some cases this took more than a year.  And, in each case the monies are still in the bank—except for those cases where operating expenses have been paid or a payment in the Kavimba Forest Reserve enterprise was made.

Related to the length of time necessary to produce viable CBO models is the array of the relationships that must be changed.  The information produced by the NRMP about these relationships is an important intermediate result which has potential applications in the whole subregion.

Within Communities:  At Chobe and Sankuyo the communities are at critical points in making fundamental decisions.  At Sankuyo the Board chair is ignoring procedures which are stipulated in the Constitution on how to deal with operators.  Members of the Trust are concerned that his actions will put their current contract at risk and will change the way the Trust is managed.  They do not know what to do but 19 members approached NRMP expressing their concern and soliciting his assistance in helping the Trust to get back on track.  At Chobe, there is confusion about how a contract was negotiated and about the roles of the members of the Trust in negotiating a contract.  In both cases, there is a failure to follow procedures that prescribe the responsibilities of the Board to the Trust and the rights of the general membership to know about and be part of the Trust’s affairs.

Among Communities:  The Chobe and Gweta Trusts include multiple villages and decisions have to be made across these villages.  These agreements and negotiations are new and people are still coming to terms with how to do it.  For example, the Village Trust Committee in Kavimba, a member of the Chobe Trust is interested in salvaging timber from a nearby Forest Reserve.  The question has come up of whether this should be an undertaking for the entire Trust (involving all five villages) or just something for Kavimba.  The members of the Trust have to determine this themselves.

Between operators and the Trusts.  At both Chobe and Sankuyo, problems have arisen over the process of dealing with operators.  At the heart of issue is how the Trusts see themselves: do they see themselves as business partners that share responsibilities as well as benefits, or, do they see themselves as beneficiaries of a project in which they share little responsibility?  At Chobe the three year contract signed with the operator last year is being renegotiated because there were misunderstandings amongst members of the Trust about what the contract contained.  The misunderstandings arose in part from the failure of the Board to read the final version of the contract.  Thus, even though the contract was signed by all concerned in the presence of GOB officials, the fact that it had not been read caused confusion.  The operator, to his credit, agreed to renegotiate.  These negotiations are currently under way and, to date, the operator has agreed to all the points requested by the Board.  Something to watch over the year will be whether the contract is respected or whether the Trust tries to get more out of the operator.  From the perspective of the operators, there are questions on whether the Trusts are reliable partners or not.  The two operators with whom we spoke were willing to train members of the Trust to be part of the operation and to invest in the enterprise.  However, they need to have assurance that the Trusts will follow procedures and live by the agreements.  This is precisely the type of situation where HATAB will be able to assist, by developing standards of operations that will foster additional trust between the communities and the private sector.

Between Trusts and the GOB.  Up to now, communities have been dependent upon the GOB for most basic services such as water and schools.  While the communities have benefited from these basic necessities, they have come at a price.  Not only do the funds come from the GOB, but the ideas and initiatives come as well.  As a consequence, communities in which Trusts are forming have had little experience in exercising decisions which have had significant consequences.  In the three Trusts noted above, each has resources generated which they can mobilize for their own priorities.  How well these resources are used depends upon decisions by the Trust, not by the GOB.

To succeed,  the Trusts also need to negotiate with the GOB and carry out their sides of the agreement.  The GOB has already devolved authority to communities.  For example, wildlife management concessions used to be negotiated between the GOB and operators and it has only been during the last few years that communities have been given exclusive use over hunting areas with the legal authority to negotiate contracts.  As a partner with the GOB as well as the operator in the management of the wildlife and veld areas, the Trust must be a responsible steward of the habitats and animals.  To date this seems to be the case, but there is still a need to monitor the management capacity of the Trusts.

As a partner with the GOB as well as operators, Trusts are developing negotiating skills.  The development of these skills requires time and practice.  The NRMP has facilitated the process of getting the Trusts and the GOB personnel together at critical stages and has contributed to building the skills.  As a recent example, the Chobe Trust is negotiating with the District Forestry Office for salvage rights to the Kavimba Forest Reserve.  This will be the first partnership between the Forestry Service and a community, and the facilitating role of the NRMP personnel has been critical.  Both sides count on the NRMP personnel to be an honest and disinterested broker whom they trust to provide advice at critical times.  And, the NRMP has conducted a market survey for products from the salvage operation which strengthens the basis for honest negotiations.

The NRMP has also contributed to the development of the GOB partnership by helping to replace suspicion with trust and confidence.  In each community we visited, we asked about the attitudes of the community members to DWNP, and in each case, we were told that peoples’ perceptions of DWNP personnel have changed over the last five years.  Before they were not welcome and were met with skepticism.  They were viewed as policemen who were sometimes draconian in their enforcement methods.  Now, some of them are seen as facilitators and are solicited to come to assist communities.  For example, a survey of communities’ views about community-based wildlife management was conducted in 1992 in the five villages of the Chobe Enclave.  Even though the DWNP had promoting the idea of a community-based project for three years, the interchanges between DWNP personnel and communities’ members reflected little confidence on the part of the communities that they would benefit from such a partnership.  For example, several people stated that the Controlled Hunting Area assigned to them did not have animals and saw that this was a plan to close better hunting areas to them.  Another said, “it is a government trap on them that if they fail to manage the quota, they will be told next year that they have failed and the quota will be withdrawn from them.”  The communities did not want to make any decisions until their councilors had advised them.  They were very unsure of what this new opportunity entailed.  They wanted more time to discuss it with each other.  They were clearly suspicious of the process and consequences.  However, when we met with the Chobe Trust people they were anxious to have both DWNP and NRMP people present.  One person told us that, from the perspective of the Trust, “DWNP had changed from Paul the prosecutor to Paul the teacher.”

However, the Trust was nervous about the possible end of NRMP technical assistance.  When asked whether the new Community Development Advisor (CDA) hired by PACT could not fill the role of the NRMP advisors, the community was openly skeptical that the Community Development Advisor could replace the NRMP team at this point in time.  They are confident that he will do his job well, but see the need for continued support from the NRMP team members.

Among Operators.  The idea of forming a partnership with communities instead of getting concessions from the GOB is new for operators.  Although the two operators with whom we spoke expressed some uncertainty about how the arrangement would work out, both thought it was a positive development and both were cautiously optimistic.  The idea of partnering with the people in whose territory people hunt seems to offer advantages to the old system.  One of the most obvious is that self-interested community members would do a better job of providing stewardship to the habitat.  But, operators are also wary of certain operators who would not play by the rules.  In both Sankuyo and Chobe, operators have tried to circumvent the tendering rules and curry favor in ways that are illegal as per the constitution of the Trusts.  They see that this misbehavior on the part of a few could ruin it for everyone.  Reportedly, the agenda of the next operators meeting includes discussions on CBO issues.  Here again, the NRMP has had the unexpected outcome of bringing the private sector together to discuss new opportunities and how they would regulate themselves.

A momentum is starting to pick up as new communities become aware of the possibilities CBNRM.  Exchange visits between communities have been fruitful in the sense that new communities are now requesting assistance to start their own resource use programs.  In effect, people are becoming convinced that examples such as Chobe and Sankuyo work.  This will reduce the amount of time required by the project to start activities in new communities, as a certain amount of trust and confidence exists because the communities can see clear examples of what CBNRM is all about.  In this context, it easier now to start up than before because the template exists.

However, NRMP should formulate a model(s) for community-based natural resource management to better articulate to government and potential partners its successful approach.  Moreover, as discussed in more detail in section 5.2, this model needs to be agreed upon, and followed by both NRMP advisors and IRCE for a unified approach.  Such a document would also be valuable for other projects in the region and throughout Africa.

More effort is also needed to promote joint ventures, perhaps by linking it with the project’s environmental education component.  If awareness of joint ventures was increased both within communities and among the private sector, there will certainly be more partnerships created.

Additional time also needs to be spent by the project investigating new veld products, conducting market sampling,  providing technical advise on markets and quality control to communities.  Also, more cost/benefit analysis that would be useful to communities needs to be done.  One of the mileposts for the project in the next two years should be develop a maturing trust such as Sankuyo or Chobe in another area, based on utilization of veld products and show how to use income to improve management and increase life styles as example for other communities.

Secondary benefits of profit distribution for secondary projects is starting to occur and will certainly increase as the trusts build up capital.  However, procedures for distribution of benefits have not been worked out.  This is a major undertaking that needs additional effort to ensure maximum spinoffs of the project, and profits for communities.  Each trust area has a broad range of options for resource use - so far project has focused on those that have the most potential according to the communities desires.  During an extension, project could focus on how profits from the first option chosen can be used to start new opportunities.  This reinvestment in new opportunities will increase the number of income generation projects and employment creation activities.

Implementation Issues

Both IRCE and NRMP work within the same communities.  NRMP, through it’s advisors and counterparts, has the technical expertise for wildlife and veld resource utilization and community development,  and is linked with national and local governments.  IRCE’s mandate is to build the institutional capacity of the trusts so they can function as independent, stable units.  Originally intended to be under the same project, linkages between the two are becoming blurred due to different approach and management styles. As stated, this is treated under section 5.2 in the discussion about project management.

Strategies for sustainability

Sustainability for community Trusts depends on an enabling body of policies and regulations and adequate support services, especially during their start-up phases. The policy work and recommendations discussed in section 3.1 will lead significantly to the sustainability of community initiatives in natural resource management.

The main issue for CBNRM sustainability is where support services will come from to assist Trusts develop better technical and organizational skills.  While DWNP is most active player in supporting CBNRM activities, it has not yet placed sufficient staff within the Community Extension Division and the community liaison positions at the district level.  Communities can receive support services from many areas: districts, government departments, consultants and NGOs.  A project strategy to foster greater support from these institutions is warranted to increase the number of potential support services for the community.

A second strategy to insure sustainability of CBNRM activities is the formation of a CBO network.  Many advisors and the CBOs themselves see a need for an independent CBO association which is rooted in the rural experience of grass roots organizations.  The CBO association or individual members, as appropriate, could help set the agenda to ensure that it meets the needs identified in their own training plans and development strategies.  There is clearly potential for a more formalized structure, but care must be taken that the network does not become an end in itself, and become more important than the goals of the individual CBO members.

There is some opposition in the NGO community to this association, as they see it as another structure to compete with them. However, a CBO network would differ greatly from a NGO umbrella organization as it would have a grassroots constituency.  The CBO network would also help prevent a situation where an outside organization becomes the “gate keeper” to resources and expertise.

Recommendations:

1.	The four member NRMP technical team of community extension and development should be extended for an additional two years.

2.	The IRCE component should also be continued for an additional two years. Staff should be increased by two additional to work specifically in direct CBO capacity-building activities.

3.	The project should continue to emphasize capacity-building and planning within the districts for community-based natural resource management.  This will help ensure that community activities become part of the country’s planning process and ensure some technical input into specific project activities.

4.  	Continued support from the project must be maintained to take community trusts from the start-up organizing stage through the establishment of routine administration of on-going projects and ability to fund and implement secondary projects from benefits received.

5.	The project should, through input from the trusts, develop general guidelines for procedures for benefit distribution from the trusts.  The general guidelines should be adapted and adopted by each separate trust.

6.	The project should assist Trusts to develop procedures and plans for the use of Trust funds.  While DWNP and project staff have a long-term vision of the benefits of CBNRM and potential uses of profits - the community themselves must develop a vision.  The project should assist the community to develop a vision of where their community would be in the future - 20 or more years.  This vision will help them work towards a common goal and provide insight on priorities for investment of Trust funds.

7.	Continue to assist the above mentioned communities with planned activities, as appropriate and as requested

3.4	NGOs involvement in Community-based Natural Resource Management

3.4.1	Background

The mid-term evaluation recommended that a flexible funding mechanism be put in place to facilitate CBNRM activities, that technical and institutional capacity for CBNRM be strengthened, and the demonstration projects should be viewed as experimental with the goal of developing an array of approaches that could be achieved, replicated and sustained.  The mid-term evaluation team also recommended that "conditions, understandings, and mechanisms be put in place for NGOs to participate effectively in the project.”

A flexible granting mechanism was mandated by the closure of the Botswana Mission and the need to reduce management burden within the new RCSA.  To conduct this new component, a Cooperative Agreement was awarded to PACT to manage the new Institutional Reinforcement for Community Empowerment (IRCE) component of the Natural Resource Management Project.   Its mandate is to assist in NGO capacity-building and training for CBNRM, establish a flexible grant mechanism to implement CBNRM, develop monitoring systems to measure impact, acceptance of CBNRM and replication of efforts and finally, to facilitate the development of an NGO umbrella structure committed to NRM.

3.4.2	Key elements and progress to date

CAPACITY BUILDING

Since its arrival IRCE has been working to build fences and partner with Botswana NGOs on the implementation of sub-grants, training exercises and the design and implementation of workshops.  Some of these NGOs, recognizing their operational constraints, engaged external consultants to evaluate their operations and make recommendations on institutional change long before IRCE had a presence in Botswana.  CORDE which offers extensive programs in NGO management, for example, has a regular self-evaluation and strategic planning process which it engages in annually.

To identify training needs in organizational development IRCE used the Organizational Capacity Assessment Tool (OCAT) developed by PACT and modified by the Botswana NGO community.   OCAT is used by NGOs to set goals for organizational capacity enhancement and to track progress towards their achievement.   After this assessment, the organizations develop formal/specific plans setting targets for organizational development or benchmarks through which organizational capacity enhancement can be measured.  Currently, several NGOs are beginning to utilize OCAT for their own monitoring and evaluation purposes. IRCE should encourage those NGOs who find the OCAT useful to undertake OCAT assessments on a regular basis to track their progress.  Throughout this process it should be born in mind that OCAT is a instrument designed for rapid participatory assessment needs to continually be revisited to ensure that organizations are on tract.  In addition to the development of OCAT,  IRCE has supported several strategic planning workshops with individual NGOs.

Eleven NGOs have opted to utilize OCAT and the results are shown in Table x.  As a result of this OCAT exercise, several individual and joint training workshops have been developed in collaboration with the Botswana training NGOs and umbrella organizations (BOCONGO and FONSAG).  The content has focused on management practices including financial management, participatory techniques, empowerment and fund raising.

Table x: Summary of OCAT results

|  | nascent | emerging | expanding | mature |
| --- | --- | --- | --- | --- |
| governance |  | 8 | 3 |  |
| management practices |  | 10 | 1 |  |
| human resources | 2 | 9 |  |  |
| financial resources |  | 9 | 2 |  |
| service delivery |  | 8 | 3 |  |
| external relations |  | 7 | 3 | 1 |
| sustainability |  | 9 | 2 |  |

source: IRCE, September 1996

Based on these findings,  it was recommended by participating NGOs that IRCE and BOCONGO develop a comprehensive training plan for all NGOs in the broad areas of leadership and governance, participatory training methodologies and techniques of improving service delivery be developed.  It was also recommended that IRCE support an assessment of NGO manpower needs and development of appropriate skills transfer techniques.  In this context, IRCE carried out an assessment of the training resources available from 16 organizations from the NGO community, parastatal organizations and international organizations.  Both generic training and specific training tailored to the needs of each NGO (and CBO) are felt to be critical components in organizational development.  The interim report is being reviewed and the next steps in this study are being developed.

Another recommendation was that IRCE promote NGOs to develop a Code of Conduct or guidelines for community development principles that might guide the NGO in their development practice.  Also, IRCE would initiate dialogue between NGOs and government/private sector and donors to facilitate resource mobilization to support NGO activities and that they continue to support organizations with externally-financed self-evaluations and strategic planning processes.

In addition to capacity-building training and networking activities, IRCE has used several novel approaches such as using a theater group for the village of XaiXai to facilitate discussions on CBNRM, providing business training opportunities in Setswana to Sankuyo via the Maun Business Training Center and, with the advise of NRMP advisors, locating experienced local firms to work with community members to map the resources, identify current uses, and to develop a plan based on potential resource uses.  Within this framework, Community Escort Guides could become monitors for resource use and the Trust could issue permits according to the plan.  This is being done in Namibia and may be worth a trip for IRCE and community members.  One spin-off of the training has been employment by Maun companies of the business trainees.  To date, the people who received the business training have not had an opportunity to use it in the Trust activities.

Botswana Orientation Center is also providing a forum for the exchange of ideas and the sharing of lessons learned through its community participation newsletter supported by IRCE.

GRANTS MANAGEMENT

To date nine of the thirteen sub-grants issued by IRCE have gone to seven NGOs (see table x) predominately to provide support for community mobilization and planning for natural resource use strategies.   Two additional grants were given to provide technical assistance for market feasibility studies and to support pilot projects.  Another two sub-grants have gone directly to CBOs and are managed by IRCE.

Several other projects are progressing through the identification, feasibility and planning stages and it is expected that they will come on stream in 1997.

Proposals for grants are assessed by the Proposal Review Committee made up of the Director IRCE, Chief of Party/NRMP and the USAID/NRMP Project Manager and representatives of the NGO community.  Proposals are reviewed, inter alia, on technical, social, institutional criteria.

Conclusions

IRCE has been receiving an increasing number of requests for support from NGOs, district government officials and community organizations.  This indicates an expanding interest in CBNRM and the types of services offered by IRCE in community mobilization, organizational development and training.  Of the thirteen sub-grants only those given to CBOs (CECT, Sankuyo, Gweta and Thusano Lefatsheng) are currently at the stage where natural resources are being utilized for the benefit of communities.

Several mechanisms are possible to support CBNRM activities.  The best (and the overarching goal of NRMP) are CBOs managing primarily on their own.   However, CBOs will need support services (marketing channels, advocacy, technical assistance or training among others) for quite some time.  These support services can be built by CBOs building partnerships in collaboration with district officials, NGOs, private enterprise or DWNP and other ministries.   However, this may lead to a dependency relationship rather than empowerment which would further disenfranchise the communities.  Where CBOs have not yet developed, or where community processes are weak, some of the best partnerships could be with rural-based NGOs with a grassroots focus (such as Kuru Development Trust).

Evidence on the ground however suggests that while the NGO community has many skills (both technical and organizational) many are not focused on building community capacity to manage their natural resources, in addition they are constrained by lack of staff and financial resources. Several NGOs have skills to offer with respect to production and utilization of resources, conservation and marketing which should be built upon. Furthermore as the NGOs develop organizationally they will be defining their mandates and capacities and may move into more and more community-based initiatives. In this context, the best role for non-rural based NGOs are providing the specific services that they specialize.  This is currently occurring with Womens Finance House who is providing their expertise on small credit schemes to Tswapong Hills.

Funding has also gone to support implementation of CBNRM  with NGO facilitation rather than NRMP directly facilitating the CBO formation and development process.  It should be noted that this approach only seems to be relevant in areas where communities are not well organized.  Where community structures are in place, there is a strong feeling on their part that they wish to be empowered through advice and training to 'go it alone". In addition the grants mechanism has been used to conduct participatory studies which will lead to better strategic choices and pave the way for monitoring implementation,  and to empower rural women through more effective utilization of natural resources.

Grants should not be used as leverage to get NGO involvement in the community activities.  As stated elsewhere in this report, support activities to CBOs must be localized.  In some areas it is not necessary, or even desirable, to have an NGO automatically become involved.  In other areas, NGO involvement provides real benefit and services to the community.  The key is that NGOs should be involved when they have a real constituency in the community and/or are providing services (training, credit services, etc.) that the community needs.

At some point IRCE needs to evaluate whether or not the training workshops, designed as a result of OCAT, are achieving the intended purposes or whether organizations are being overloaded with so much information that they are unable to take the lessons learned home and transfer them into implementation on the ground.   Gweta Trust is the only grant activity evaluated to date. The quality of the evaluation and its recommendations for the further development of this initiative, considered valid by all parties, suggests the need for more formal evaluation of sub-grants.

IRCE grants mechanism does not cover USAID environmental impact assessment regulations.  Although the most or all of the grants would probably receive a categorical exclusion, a procedure should be established to ensure adherence to the regulations.  In this context, IRCE should request USAID for assistance from the regional support office (REDSO) to assist it in establishing assessment procedures.

Within the PACT Cooperative Agreement there are a couple of incorrect assumptions that need to be rectified.  First, concerning the ceiling for the amount of grants it states “other factors to consider are absorptive capacity of the NGO community and the number of grants that can be effectively handled by PACT and eventually the NGO structure.”  This is potentially limitless and misses the whole CBO context in which the project operates.  It is the absorptive capacity of the CBOs that matter under the NRMP.  The second is that an “NGO Structure should eventually have the mandate and the capacity to gradually assume the role currently played by NRMP.”  No one structure will take over the mandate of NRMP as it is multi-sectoral and a large amount of partners are needed to continue the CBNRM process.  Moreover, NGOs do not have the mandate over land use - the most critical aspect of instilling responsibility for natural resource management with the communities.  Finally, the districts are the most obvious entry point towards assuring overall support to community structures within their boundaries.  This is not to say NGOs don’t have a role, their role is vital and they could provide services that may be lacking within government agencies.  Again, this is evidenced in the Womens Home Finance providing expertise on credit and Maun Business Center that can provide specific specialized training in business skills.

Strategies for Sustainability

One of IRCE’s mandates is to create an umbrella “NGO structure” committed to CBNRM.  A working group of NGOs was formed on behalf of USAID by NGO/PVO/NRMS Project to develop a time line and work plan which is now being used as the basis for discussion with other donors notably DANCED.  It is hoped that DANCED and USAID will collaborate to ensure that approaches and methods being employed support rather than contradict one another.

The development of an NGO structure would evolve from the consultative process among NGOs working on the NRM sector.  This 'NGO structure" is purposely not defined at this stage but it could be a consortium, a subcommittee of the existing NGO coordinating council, a single NGO, or a paid secretariat".  It appears to the evaluation team that the “NGO Structure” is worthy of support and can provide benefits, in the long term, for community-based natural resource management.  However, it can diverge from the main goals of NRMP.  A better strategy for sustainability of CBNRM is building the capacity of CBOs themselves to manage their own affairs. IRCEs allocation of resources should reflect this.

Implementation Issues

As the project completion date nears, IRCE has felt pressure to spend its grant money before this date.  This pressure, real or imagined, may obviously lead to funding activities that may not be the appropriate or adequately thought out.  While the evaluation team doesn’t feel this occurred, the danger is there and should be dispelled.

As with the grants, the NGO component of IRCE has wrought some confusion among the project.  While NRMP advisors are working directly with communities towards community empowerment, the Institutional Reinforcement for Community Empowerment component focuses of this goal through NGOs.  Part of this confusion is caused by the different use of jargon but mostly it is caused, again, by the lack of a clear, unified vision or model agreed to by both IRCE and NRMP.

Recommendations:

1	IRCE should continue for two additional years with its dual mandate of building CBO capacity for CBNRM and grant management.

2.	IRCE must stay focused on the goal of increasing communities capabilities for self management and therefore, emphasis on CBOs.

3.	IRCE should facilitate, as requested, an eventual “NGO Structure” but the establishment of one should not be considered as a “deliverable.”

4.	IRCE should actively facilitate an eventual independent CBO Structure and the establishment of one should be considered as a deliverable.

5.	The grants management procedures in place should become more transparent and ensure technical guidance from NRMP advisors.  In this regard the following is recommended.

A.	Criteria for proposals to be considered for funding should be “tightened up” to ensure proposals directly relate to NRMPs goals and objectives and that if a new partner is involved, it has a constituency in the CBO or is providing a relevant service.

B. 	The Proposal Review Committee should be expanded to include NRMP counterparts with assistance from the advisors and chaired by the USAID Project Manager.  Decisions of this Committee should be final.

C.	The Proposal Review Committee should pay particular attention that proposals do not take away the responsibility for CBNRM from the communities, acts as a surrogate for community involvement or provides capital input that exceeds the absorptive capacity of the community. The Committee should also ensure proposals meet M&E and environmental impact assessment requirements.

6.	IRCE should continue participatory monitoring of the institutional and technical capacity development of NGOs using OCAT and develop a similar instrument for monitoring CBOs.

7.	IRCE should ensure that M&E systems are part of every sub-grant.  This would include engaging NGOs and CBOs in the monitoring of income impacts and attitudes towards sustainable utilization. Regular reporting on the status of sub-grants should be done by IRCE and this information should be made available to the Proposal Review Committee.

8.	IRCE should also ensure that EIAs are part of every sub-grant in accordance with USAID regulations and Botswana regulations.  In this regard, it is suggested that IRCE request assistance through USAID for REDSO Nairobi to give assistance.

9.	Training and workshop activities should include regular follow-up visits to monitor skills applications and impacts.

19.	IRCE, USAID, NRMP should commission case studies on some of the cross cutting issues/ unintended consequences so that benefits of the lessons learned and models developed can be fully shared throughout Botswana and the region.  Examples of case studies could include:

-the different models and approaches being utilized for CBNRM

- 	the governance impacts, changing relationships of villagers to each other, villages to each other, communities to government, the way of doing business in committees other than trust committees , and the impact of additional members of communities taking on leadership and planning roles.

3.5	Personnel Planning and Training Component

3.5.1 Background

The Personnel Planning and Training Component (Amendment 3) was added to support project activities at the recommendation of the mid-term evaluation team in 1993.  The purpose of this component is to strengthen the human resource capacity of DWNP to engage in sustainable natural resource activities.  The strategy was to increase the number and caliber of qualified professionals within the department through long and short term staff training, to promote efficient management within DWNP through the application of human resource development techniques and to revitalize both the facilities and curriculum at BWTI for systematically training all game scouts at the district level in critical wildlife management and community extension skills.  Transformation within DWNP was needed to create a cadre of well-trained professionals who were able to establish public confidence in the department as a service organization and facilitate institutional linkages between government, NGOs and the private sector at local, district and national levels in order to integrate the conservation and development of natural resources.

3.5.2 Key Elements and Progress to Date

Table 1. Summary of Activities for HRDU and BWTI

| Activity | Status at Final Evaluation |
| --- | --- |
| Training Needs Assessment | Completed 314 assessments in 21 months with less than 10% of officers not participating. Scores currently used for selection and placement in IBT and Certificate courses at BWTI. |
| Annual Training Plan | Several division heads using techniques learned in a workshop and follow-up meetings. With a short term consultant developed DWNP’s short term training plan. This plan was changed by Administration without consultation of Division head. DWNP did not submit completed plan to DPSM for 1996, therefore staff training opportunities for 1997 may not be allocated (except for USAID sponsorship slots which were submitted separately). |
| Supervisory Training Workshop | Successful, five-day supervisors seminar attended by 30 participants to review the BWTI training programmes, solicit suggestions from DWNP professionals and discuss the development of regional in-service training programmes for junior staff. Seven areas were suggested for specialized training including: public relations, PAC, computer training, statistics- research /monitoring, licensing procedures, community extension education and conservation education. |
| Rehabilitation of BWTI facilities | Completed key structures and DABS certified. Renovation and use of library facilities very successful. Problematic areas are laboratory, herbarium/museum and recreational facilities which were not the responsibility of NRMP. |
| Job Descriptions | Completed and given to Director but not yet approved by DPSM. Used by several senior game wardens and assistant directors within DWNP for staff deployment, skills and qualifications needed for a given position and decisions of training needs for division/unit. |
| Career Path Development Plan | New and under development with participation by division and unit heads to assemble in relation to scheme of service. Senior Game Wardens using for a transparent system of progression for staff within a particular division, but not distributed uniformly across DWNP by Administration |
| Electronic Personnel Files | Previously all done manually and difficult to keep consolidated and updated. Not used in decision-making. Seen as a very useful service of Administration by several senior game wardens and assistant directors within DWNP to keep regularly updated and accurate lists of staff by district, used in decision-making for training, promotion and deployment. |

| Activity | Status at Final Evaluation |
| --- | --- |
| Recruitment Process (Pre-service Training) | Selective pre-service training program successfully established at BWTI for new DWNP game scout recruits using DPSM guidelines. New recruits immediately complete IBT and are deployed to their posts knowing what the mission of DWNP is as well as having the necessary skills to carry out their job responsibilities. Further attention needed for streamlining/institutionalization of Administration unit procedures for recruitment process and timely deployment of newly trained staff. DWNP recruitment process for other positions remains problematic due to conflict of Administration/DPSM procedures. |
| International Training | Excellent logistical support and correspondence with staff on long-term training by advisor. Problematic selection process and budgeting of transportation expenses resulted in missed training opportunities for several DWNP staff. Training needs assessment indicated that supervisory staff needed leadership, management and development planning skills. More programs focused on technical natural resource management areas. Advanced training as follows: CBO/NGO (5), Research (3), M & U (14), Conservation Education (4), Parks (8), Administration (3), Finance (1), and Forestry (1). See attached list in Appendix. Some of the staff on long term training programs have thesis topics which are directly relevant to CBNRM issues such as: 1) An assessment of formal and non-formal environmental education programming in rural communities in Botswana and 2) Indigenous wildlife management practices and contribution to community-based natural resource management. For other staff that have had a more traditional wildlife management research oriented training there needs to be a reintegration plan for application of skills within DWNP to CBNRM upon return with report sent to DPSM. |
| Specialized Problem Animal Control Training Courses (PAC) | New unit developed and professionalism noted by senior DWNP staff. Excellent groundwork and foundation established for a service-oriented extension unit within DWNP in PAC and Trackers. Total of 39 PAC officers trained. Instructors trained who have now implemented three courses on their own. Need animals for field component to be effective. PAC training for communities requires start-up. |

| Activity | Status at Final Evaluation |
| --- | --- |
| Induction & Basic Training | Designed and conducted six 8-week training courses for 151 game scouts with 85% pass rate. Seventh course in progress and responsibility/leadership for course by Batswana BWTI Training Officers. The IBT is a comprehensive field and classroom course with hands-on approaches to wildlife management. |
| Curriculum Workshop | Well attended by DWNP staff and others. Used as a basis for participatory development of curriculum in use at BWTI. |
| Train the Trainer Workshop | A thorough, intensive Train the Trainer course was held at BWTI from Oct 6- Nov. 25, 1995 with 12 Training Officers participating. The workshop included teaching methods, lesson planning and hands-on micro teaching exercises which were peer evaluated. Workshop participants indicated that they found the workshop to be very useful. However, the staff were greatly disappointed by the inclusion of information from personal interviews in the final report. |
| Teaching Methods Workshop | Problematic attendance due to conflict with classes going on at the time. |
| Certificate Training Program | Selection process for admittance into program done by performance on assessment. Minimum score of 50% now a requirement. Revised curriculum with field emphasis as opposed to solely theoretical training started. Eight new modules with lesson notes and field applications include: Departmental Objectives, Field Skills, Introduction to Natural Sciences, Introduction to Natural Resource Management, Parks Management, Community Extension Services, Management & Utilization and Leadership & Supervisory Skills. Currently the program is a semester based timetable, thereby making it impossible for other staff to enroll in a specialized subject area for a short, concentrated period of time. Relevant field projects such as visitation patterns for Gaborone Game Reserve are conducted and supervised by BWTI staff, not supervisors. |

Conclusions

The combined coordination of Human Resource Development Unit with the Botswana Wildlife Training Institute has resulted in a substantial restructuring of DWNP towards personnel training and capacity-building.  Appropriate training has been systematically provided for non-certificated tenured staff (with some limitations due to DPSM regulations) and new recruits through a comprehensive Induction and Basic Training program and selective pre-service training.  A new revised national certificate program is underway, but some concerns must be addressed in order for the program to effectively meet the needs of the department.  Namely, the length of time required to complete the program in relation to the number of people who need training creates a bottleneck, lack of appropriate logistical arrangements by support staff seriously undermine the training effort, and collaboration with supervisors for on-the-job application of skills during the field projects need further attention.  Educational enhancement, career path alignment and the development of specialized in-service training are key areas for further concentration of efforts which require coordination by BWTI staff, Conservation Education and Community Extension units with HRDU.  Excellent examples exist which should be built upon for meeting in-service and specialized course needs of the department.  For example, the Conservation Education unit's programs in conservation policy have provided critical policy information to district offices using innovative methods.  A second outstanding example of practical, specialized in-service training is the development of a PAC unit which included selective recruitment, training of instructors, transition of responsibility for program implementation to qualified Batswana counterparts from the advisor and successful training of DWNP game scouts as Problem Animal Control officers.  There is a clear trend in all training components towards a transition in responsibilities from NRMP advisors to DWNP staff which is critical for sustainability of the programs.  Procedures are needed within DWNP for continued institutional support of such programs.

HRDU

Changing attitudes and procedures that have developed over many years is a very difficult process.  It requires consistent and firm support from top management in order for any HRDU effort to be effective.  The advisors services were not used to full capacity.  As one Principal Game Warden said, "We have lost by not paying enough attention and recognizing the importance of this."  Many DWNP officers expressed concern over how the information assembled (i.e. personnel records and job descriptions) will be managed after advisor leaves.  Several DWNP professionals hoped that the new Assistant Director of Administration would be able to facilitate and maintain new services.  In a very short time, she has already designed and analyzed a questionnaire on efficiency and professionalism of Administration unit with the intention of instituting improvements.  A transition period required in which leadership and responsibility to update, maintain, interpret and provide critical personnel services to division heads within DWNP is taken over by several qualified Administration staff.  Management and computer training is required for several staff in order to do this.  There should be a review of linkages between the HRDU and the ODA Administrative support activity

Implementation issues

Constraints in implementing the PPT effort included high turnover rates of personnel within DWNP and DPSM, frequent changes, cumbersome and problematic coordination between DWNP, MCI and DPSM, training and delays in assignment of counterparts, incompatibility of proposed HRD strategies (Incentives/Probation/Competitive Selection/Mid-level recruitment) with DPSM procedures and non-implementation of compatible HRD techniques by certain DWNP administration staff.

Recommendations

1) 	Extend the current HRDU advisor for 1 year from end of his contract. Suggest changing the HRDU focus to a Professional Development and Training Advisor due to increased emphasis and need for coordination of training in relation to career path development within the department.  Areas identified by Administration unit as priorities include: a) skills transfer on management and use of computerized personnel records and implementation of performance standards for job descriptions, b) design and implementation of department training plan and c) team building within the Administration unit towards creating a service orientation.

2)	 DWNP/DPSM should officially assign the Assistant Director of Administration as a counterpart to the advisor.

3) 	The computer records post should be immediately filled by a qualified person of the appropriate rank and authority. Several officers within the Administration unit, however should be competently trained to use the records.

4)	Increased emphasis and selectivity of training towards community development/extension orientation and administration skills as opposed to traditional wildlife management technical subjects as outlined in the training needs assessment.

5) 	Selection process for training opportunities needs to be revisited by senior staff within DWNP and DPSM so that the appropriate staff are trained to further the capacity of the department to implement its mission statement.  An action plan by the trainee and supervisor of how the training will be used on the job should be developed and evaluation made within six months of return to service.

6) 	Continue and refine pre-service training program. For example, adding a pretest to the recruitment process would prescreen applicant and minimize cost.

7) 	Use local contractors to supply in-house services for training of administration unit and senior district supervisory staff in management principles, team-building and computers. This should not be classroom training, but rather practical, on-the-job training that contributes to solving current problems with evaluation and follow-up to insure skills transfer.

8) 	Continue to interface with other donor and government agency HRDU efforts on organizational development for the implementation of job descriptions, career path development procedures and performance standards.

BWTI

There has been a complete transformation of the facilities at BWTI, quality and focus of training effort and capacity of instructors.  Curriculum revision was a participatory process involving all levels within DWNP.  New involvement of professionals within DWNP in training as subject matter specialists was seen as valuable both by BWTI training officers and by DWNP staff.  Professionals within DWNP see BWTI as an institute that is playing a critical role in raising the performance standards of the department.  As one Senior Game Warden said, "BWTI is fantastic!  They really learn and when they come back they want to apply the new skills."  For example, a BWTI-IBT graduate at Gemsbok National Park wrote to the Senior Game Warden that before he went to IBT he could not tell tourists the names of animals/plants or describe the ecology of the area.  Now, he is able to use the new interpretive skills to describe the role of tsama melon in the ecosystem.  Another BWTI-IBT graduate was leading school groups through the termite trail at Gaborone Game Reserve at the request of teachers in the area. In this case, the IBT built upon previous training she had with the environmental education component of the project.  Unfortunately examples such as these of on-the-job application of skills learned in the program are sporadic.  An evaluation of on-the-job application of skills is currently under review via face-to-face interviews and questionnaires completed by supervisors and IBT graduates.   Success of the training will be undermined if supervisors at the districts do not support the application of the newly acquired skills on the job. The BWTI newsletter was seen as valuable by IBT graduates and DWNP professionals which helps sustain awareness and interest in the value of the program to the department.  However, institutional mechanisms are critically needed to support skills application or the program will not meet its objective of upgrading the capability of the department.

Implementation Issues

On-the-job skills application by new graduates has surfaced as a potential problem.  Supervisors need support in placing demands on BWTI graduates to use the skills that they have learned on-the-job.  The Training Needs Assessment clearly pointed out the supervisors were much more conversant with technical subjects than management skills such as development planning, leadership, and supervision.  Continual problems with support personnel for timely and critical logistical support, vehicle maintenance and supplies for field component severely undermines program objectives and will jeopardize the quality of the program during the transition period if attention is not given to this aspect of the institution.  Credibility of advisor position was undermined by problematic administration of first advisor in the position.

Recommendations

1. 	Continue two BWTI instructors for two years with continued emphasis on transition of all courses (pre-service, IBT, certificate).  Advisors should have technical backstopping function and collaboration on evaluation of certificate course, training of instructors, and development of specialized short courses/modules that are linked to Certificate program.

2. 	Continue transition for BWTI advisor until end of current contract with focus on: a) completion and acceptance of the Authority and Discipline (or Operations) Manual by BWTI, DWNP and DPSM, b) design of an academic enhancement program (ie. night-time tutoring offered and required for game scouts in basic English and math skills at the library) and c) evaluation of certificate program and alternatives for streamlining it.

3.	Continue transition of responsibility for IBT course to DWNP Training Officers including logistics, instruction, process evaluation, editing and production of the BWTI newsletter and on-the-job evaluations.  The transition of secretarial support for courses also needs to be addressed.

4. 	DWNP training staff need practical field instruction experience.  Training should be sought through relevant intensive short courses or through structured internships with exceptional wildlife management departments in the region.

5. 	There is a need for an BWTI administrative liaison at Headquarters to coordinate follow-through of supplies, administration, paperwork, recruitment, field placement etc to overcome bureaucratic obstacles. Should work with both Administration unit, PPT advisor, HRDU, Director, principal and BWTI instructors.

6. 	There is a clear need for short, local management training of support personnel and a re-examination of DPSM procedure with regards to the requirements of implementing pre-service training courses.

7.	 Field-based training programs require a logistical coordinator position.  DWNP should explore creating such a position at BWTI with the appropriate rank and authority to coordinate all the logistical arrangements for field exercises.

8.	Field projects need to be more clearly defined, shared and supervised to maximize learning, accountability and knowledge gained within DWNP. (ie. The skills within the department could be shared via a mentorship program.)

9. 	Continue supervisors workshop as a regular component of field practicals of certificate course.

10. 	The two-year certificate course with the present facility only produces twenty-five graduates. Examine alternative path of taking specialized intensive short courses which accumulate towards a certificate and/or promotion. Use assessment scores for placement.  Use training needs analysis for prioritizing development of special modules.

11.	 Need to secure accreditation of certificate program officially from DPSM within Botswana and relevant wildlife training institutes in the region.

12. 	Use or coordinate with trained PAC instructors in M & U for the BWTI specialized module.

13. 	Effective qualified PAC officers should have experience working with animals in order to service communities, otherwise there is a tremendous safety risk to both the officers and the public. The PAC unit in M & U in consultation with the NRMP advisor should be given full support from Headquarters and the districts in designing procedures for appropriate training venues with animals.

14. 	Coordinate community escort guide training to interface with BWTI, if possible, and extend training to incorporate monitoring skills in all natural resource utilization.

3.6	Formal and Non-formal Environmental Education

3.6.1	Background of Formal Environmental Education Activities

The initial emphasis of the NRMP's environmental education effort was on the formal sector working in conjunction with the Ministry  of Education.  The purpose was to coordinate the infusion of new environmental education concepts into the curriculum using a broad based approach that included activities at the primary, secondary, teacher training and university levels.  An environmental education advisor was employed to coordinate these activities from October 1991 to March 1995. A plethora of activities were initiated including a National Planning Conference for Environmental Education, a thorough environmental education needs assessment at the primary, secondary and teacher training colleges, development of supplementary environmental education teaching materials, production of teaching videos by CDD/TVE to support the National Conservation Strategy and a series of teachers training workshops in conjunction with a multitude of agencies at the Gaborone Game Reserve.  After the conclusion of the environmental education advisor's service, a series of three consultancies to support a new environmental education officer within CDD were planned.  The consultancies have been delayed in anticipation of the post being filled.

In December 1995, the status and future sustainability of environmental education activities within the Ministry of Education were reviewed.  Many of the projects initiated by the NRMP were at a standstill, yet hovered on the verge of completion.  A major shift in educational policy occurred in 1993 which among other things completely revised the entire junior secondary curriculum as well as incorporated a student-centered approach for all subjects.  In the flurry of activity needed to completely revise the entire curriculum, the initial environmental education momentum was lost as the educational community shifted its focus towards implementing the new policy.  As of 1995, the curriculum review programme for the Primary Teacher Training Colleges, College of Education and in-service training were delayed when the Basic Education Consolidation project closed.

3.6.2 	Key Elements and Progress to Date

Table 1. Summary of Environmental Education Activities (Phase I Formal Emphasis)

| Activity | Status at Final Evaluation |
| --- | --- |
| National Planning Conference for Environmental Education | The Ministry of Education, the Faculty of Education, UB and the Kalahari Conservation Society organized the national conference which was sponsored by NRMP/USAID, SIDA and UNESCO. Policy recommendations from the conference were adopted by the Curriculum Development Division in the MoE and NRMP as program guidelines including curriculum development, needs assessments, teacher workshops and a National Tertiary Environmental Panel. |
| Needs Assessment Studies | Comprehensive needs assessments on the status of environmental education themes and teaching techniques were completed for primary school teachers, JSS teachers, and PTTC Lecturers. The findings were reported to MoE, TTC and Faculty of Education at UB. |

| Pre & In-Service Teacher Training | The NRMP in collaboration with The Faculty of Education-UB, KCS, CDD/MoE, DWNP officers, Peace Corps Volunteers and others implemented seven skills-oriented and project method training workshops for teachers, wildlife club advisors and game scouts with a total of 250+ participants at Gaborone game reserve. The Environmental Education Center at the reserve has been closed for 18+ months. Plans for renovating the center and building a tent campsite which could be used for teacher training and school groups have been discussed. Even without the center operating, school groups continue to use the reserve for game drives and group discussions at the picnic area. Recently, DWNP game scouts with support from Faculty of Education-UB used the reserve and activities book for school projects on termites in response to teachers requests for services. |
| --- | --- |
| Environmental Awareness through Functional Literacy | A needs assessment of environmental education topics used in the non-formal education sector including Extension Educators, Literacy Assistants and Literacy Group Leaders was completed in 1992/93. The results are still under review. |
| Environmental Education Reference Materials | A list of reference materials was developed, ordered and distributed to the 14 environmental education centers, Primary Teacher Training Colleges and Colleges of Education. |

| Materials Development | The Teacher's Resource Handbook for Environmental Education that was originally developed in 1992 has been extensively reviewed by CDD, but not been printed or distributed. The Environmental Education Reader developed by junior secondary students has been at the TAPU since 1995 for illustration and printing. The Environmental Education Charts have not been evaluated for use. A large-print Environmental Education Calendar of student activities and games was printed for 1995, but not continued. |
| --- | --- |
| NCS/TVE Video Series | Over a two year period, the CDD in conjunction with TVE produced a series of five videos with teacher notes to support the National Conservation Strategy in response to recommendations of the 1991 Environmental Education conference. The videos have been duplicated and will be disseminated through a series of teacher workshops when the teacher notes have been completed. |
| CDD Environmental Education Officer Position | This newly created junior level (C1) post within CDD remains unfilled. It has been advertised several times over the last three years, but likely candidates have taken other higher-paid teaching positions. Discussions continue on how to fill the post. |

Conclusions

Environmental education is a topic that in the past has traditionally fallen outside of the formal curriculum in most countries.  Integration and awareness building are long-term processes (10-20 years) that require coordination and dedication by a wide array of professionals including teachers, publishers, curriculum development specialists, NGOs, government planners and natural resource professionals.  The mid-term evaluation of the NRMP recognized that focusing on the integration of environmental education within the curriculum was a necessary, but slow, meticulous process that would take many years to yield visible results to support CBNRM activities.  Within the NRMP, a tremendous number of environmental education activities were tried based on strategies that have been used successfully in environmental education campaigns internationally.  The original vision of the scope of work for the Environmental Education advisor and the Ministry of Education included a breadth and depth of activities that far exceeded the time frame and personnel available for implementation and follow-through.  Sustainability at the original level of effort is clearly not possible, nor is it necessarily needed as participating organizations re-adapt the methods to fit their circumstances.

The wide range of activities supported by the NRMP over several years in collaboration with a multitude of government, private and non-government organizations have acted as a catalyst and support to the development of environmental education activities in Botswana.  For example, Action magazine published an edition devoted to ecosystems, an effective shopping bag campaign focused attention on recycling, and world environment day expanded during this period to a full month of activities including activities such as essay contests, conservation spelling bees, and radio programs.  The University of Botswana Environmental Education Project (UBEEP) coordinated by the Faculty of Education-UB/SIDA is currently engaged in training workshops in conjunction with CDD, teacher training colleges, MoE officers and inspectors.  This project builds on the earlier approach for pre-service and in-service training activities of NRMP.

A few examples of the scope of activities and future plans for the environmental education community in Botswana include a recent series of meetings and workshops on implementing the NCS, plans for the creation of an affiliate chapter to the well-known, regional Environmental Education Association of Southern Africa (EEASA), and the possibility of hosting the national conference for EEASA in 1998 which would be a tremendous opportunity to share CBNRM activities within the region.  It is very promising that the NCS coordinating committee on environmental education is such a broad-based task force with representatives from government (MoE, MoA, DWNP, University of Botswana, water authorities, councils and others), NGOs (Kalahari Conservation Society, Conservation International, FONSAG, Thusano Lefatsheng, Veld Products Research, Association of Wildlife Clubs, and others) and public interest.  Highlights of a few of the short-term actions include partnerships and support sought from MoE/Association of Wildlife Clubs for in-service training and promotion of events such as Desertification Day and National Tree Planting Day.  Radio, media information campaigns, and in service training seminars are the types of activities envisioned for partnerships between DWNP, Kalahari Conservation Society, Conservation International, Association of Wildlife Clubs and Chobe Wildlife Trust.

Implementation Issues

Constraints to rapid and efficient implementation of project activities included personnel turnover and study leaves, lack of a designated environmental education counterpart for the advisor, problematic coordination and organization of design teams, difficulties in establishing institutional linkages that could support the activities after the advisor left, scheduling arrangements with government printers, cumbersome communication and coordination of activities between ministries (Ministry of Education and Ministry of Commerce and Industry/DWNP) and private firms and a marked shift in educational policy.

Recommendations

Many of the people interviewed for this evaluation expressed their concern that the Government of Botswana could lose a valuable resource if the environmental education materials that were developed under the auspices of NRMP are not finalized and distributed.  The formal education sector does not at this time need further project support.  When the new environmental education officer at CDD has been hired, s/he has reference materials, wide support from the NGO and educational community and several projects lined up and ready to go including the NCS video series, Environmental Education reader, Teachers Resource Handbook in Environmental Education, and a template of useful games and activities in the 1995 Environmental Education Calendar which could be reproduced as a booklet.  CDD in conjunction with the UBEEP project and the Faculty of Education-UB could generate lessons learned and capitalize on experience gained regarding which environmental education strategies were effective, a follow-up sample of teachers who participated in the wide range of environmental education activities could be conducted to measure how the workshops, conferences and materials stimulated them to infuse environmental education in their teaching programs.  It will be important to document how activities and perceptions have changed in relation to the baseline needs assessments that were done in 1992.  This type of project would make an excellent Masters level thesis.

Build upon linkages and networking between environmental education activities and the efforts of the Conservation Education division to generate a multiplier effect for the spread of specific CBO/CBNRM information by selectively using the posters, videos and booklets developed by the Conservation Education unit of DWNP.  For example, use and impact of the NCS videos could be capitalized on in several cases if more copies of the videos (particularly the Veld products one) are available to other groups to extend through the DWNP Conservation Education, CBO and NGO networks instead of being limited primarily to the formal education sector.  Several options exist:

1) 	Use of the Veld products video by NGOs (Thusano Lefatsheng/Veld Products Research) with stop video techniques at capacity-building workshops, BWTI and by the Conservation Education division of DWNP.

2) 	Coordinate and maximize the multiplier effect of teachers using the NCS videos by having a DWNP representative provide a brief presentation using participatory methods at already organized teacher training events.  This would be valuable skills practice for new community liaison officers and/or interested game scouts and would require a minimum of effort or cost.

3) 	Coordinate distribution of materials with the environmental education efforts at Mokolodi and other active centers.  This facility services 7,000 children-days/yr including teachers.  Distribution of materials (NCS videos, posters) to their staff would again increase the multiplier effect with a minimum of cost or staff effort.

4)	 The potential exists for BWTI/DWNP, NGOs, CBOs for participation at the 1998 regional environmental education conference. Development of a display and brief (1 page) examples with one or two photographs of the different Veld products/Wildlife utilization efforts would be useful products to share both within the educational community nationally and in the region.

3.6.3 Background of Conservation Education Activities

In response to recommendations of the project's mid-term evaluation, a non-formal education advisor was recruited in October 1995 to build the capacity within the Conservation Education Division of DWNP to design and disseminate educational materials at a national scale on the departments new policies and practices.  This effort was seen as complementary to environmental education activities within MoE and viewed as strategic support for CBNRM/CBOs at the district and community level in the rural areas.  In nine months, the team has been extremely effective in reaching critical stakeholders with relevant materials.  A series of district level meetings for DWNP staff, NGOs and District authorities have been held which use innovative extension techniques, booklets and posters in English and Setswana.  Current policies discussed in the workshops are: Joint Venture Guidelines, Wildlife Management Areas, Controlled Hunting Areas, Wildlife Quotas, the Botswana National Conservation Strategy, the Wildlife Conservation and National Parks Act of 1992, Tourism Policy and Wildlife Conservation Policy.

3.6.4 Key Elements and Progress to Date

Table 2. Summary of Conservation Education Activities (Phase II Non-Formal Emphasis)

| Activity | Status at Final Evaluation |
| --- | --- |
| Develop a cadre of well-trained extension staff within DWNP | Currently six trained staff located in Gaborone, Tshabong, Ghanzi and Maun. Transition of responsibility of training already shifted to DWNP staff from advisor. Need broader array of DWNP staff to completely take responsibility for implementation of workshops so that advisor and counterpart can concentrate on developing staff training courses on production methods, design of a mechanism or procedures needed for district follow-up, and video production. |
| Training Evaluation Workshop | Excellent coordination with BWTI training event for more efficient use of resources and time for reaching 17 DWNP District heads with policy information and materials. |

| Activities | Status at Final Evaluation |
| --- | --- |
| Materials Development | Sets of large, laminated posters on WMAs, CHAs and quotas were developed and distributed to DWNP district offices. Training provided in the use of the posters at all workshops. Three limitations for the present set of posters include: 1) some DWNP staff are hesitant to use some of the posters because they transmit a controversial message for a non-literate audience which requires advanced facilitation skills to manage effectively, 2) bulkiness makes them difficult to hang on the wall or transport and 3) cost prohibited large numbers of posters from being produced. Extremely useful booklets in English and Setswana on CHAs, WMAs, Quotas and Joint Venture Guidelines have been reprinted already three times (21,000+) and there is still a demand for more. An interactive video in Setswana with English subtitles describing what CBNRM is, why it is important, and how to implement different projects together with examples of successes and management options of current CBNRM activities is under production. Radio broadcasts in are in the planning stage |

| Activities | Status at Final Evaluation |
| --- | --- |
| Wildlife Management Policy Workshops | Four workshops in Ghanzi, Tshabong, Molepolole and Gaborone with a total of 102 DWNP staff. Each participant received file with all relevant policy documents, innovative training techniques such as joint venture role play and land-use mapping exercise, as well as training in how to use posters. Coordination with HRDU to record workshop participation for officers. Ghanzi district has initiated staff training to discuss implementation of concepts as a result of initial workshop. Requests for follow-up workshops, further training and support by Ghanzi and Molepolole. Need to localize message in each district for actual implementation. |
| Policy Workshops with NGOs, CBOs and teachers | Tshabong-Joint KCS/DWNP function. Very successful feedback from district authorities in Tschabong with list of 23 recommended actions that included the formation of a local conservation committee to explore and review tourism potential, fencing, CHAs, WMAs and CBNRM options. Second workshop with elected officials indicated that in areas where policies have not been finalized they are not ready to discuss these issues. Maun-Joint workshop with CBOs and NGOs in cooperation with IRCE. Mokolodi-Joint workshop with Faculty of Education-UB pre-service teachers and DWNP staff. |

Conclusions:

A vibrant, but skeletonal staff has had a tremendous direct impact for CBO/CBNRM publicity and clarification of steps towards implementation of the concepts. They are currently called from all over the country with requests for information. To date, due to limited human resources, they have been concentrating in the southern and western areas of the country.  The initial strategy has focused on awareness-building and knowledge of policies first for DWNP staff followed by workshops with district leaders, teachers as well as NGO and CBO representatives.  Excellent coordination and collaboration by the team with organized events of other organizations in order to efficiently reach target audiences.  For example, joint organization of workshops with NGOs have resulted in reaching representatives from more than 39 different organizations (see appendix).  The team uses thorough preparation techniques for workshop organization.  For example, they invite staff for future planned events to participate in an earlier workshop so that they have a clear vision of the scope of activities and logistical needs for holding a workshop in their area.  For actual implementation of concepts there is a need for follow-up visits and localized information on gazettements, boundaries, and sustainable utilization of resources.  For example, in Tshabong the community listed putting up signs indicating Wildlife Management Areas and Controlled Hunting Areas as a recommended action following the workshop.  The team's work with workshops of elected officials indicates that the discussion of policy issues may in some cases be dependent on finalization of district gazettement.

Implementation Issues:

Currently, there are insufficient staff to meet the demands placed on the unit for development of materials, design and implementation of workshops, critical follow-up visits to support district officials and NGOs, and training for DWNP officers on policy issues.  Given the high demand and need for these activities, there must be a corresponding increase in budget allocations from DWNP for workshops and materials as well as more staff seconded to the unit.  There have been some delays and logistical problems due to the timing and distribution of funds by the Administration unit (DWNP).  Budgetary planning and more efficient distribution mechanisms are needed.

Recommendations

The conservation education component has had a direct impact in a very short period of time.  This critical communication and extension function to support CBNRM/CBO and relevant NGO activities definitely needs to be bolstered.  Future activities should continue to target audiences that are known to have a multiplier effect (ie NGOs, teachers, DWNP staff, District officials), however quick extension follow-up is needed to maintain momentum. Networking with NGOs and the formal education sector has thus far been very successful to overcome constraints of the government sector for quick, efficient responses. Strategic networking with selected organizations will continue to foster sustainability of the effort.

The aim of this communication effort is for all CBNRM stakeholders to fully understand their rights, roles and responsibilities.  Awareness is a first step towards implementation of policy.   In order to move from awareness to actual implementation, the Government of Botswana needs to quickly review institutional, manpower and budgeting allocations required given that 23% of the country's land area is in Wildlife Management Areas. There is a clear need for capacity-building at the district and community levels.

1.	Extend the contract of the current Conservation Education advisor for two years.

2. 	Permanently assign more DWNP staff (game warden or above with at least one per district)to the Conservation Education and/or newly-created Extension unit for training by the advisor and counterpart to form a information dissemination team.  The members of this team need to be posted to key districts throughout the country while the advisor and his counterpart should be mobile.

3. 	Continued strong support by the director and senior staff to emphasize the necessity, importance, and visibility of Conservation Education effort throughout the department.  Widely promote the concept that the department now has an extension function which means that all staff are expected to use and distribute materials when they participate in public forums as well as provide follow-up services and answer questions by the public following events. Participation should continue to be documented by HRDU and used in both promotion decisions and selection for further training.

4.	Design and implement staff training in facilitator skills, production methods, knowledge of CBNRM options and veld products to widen the team from the current six officers.

5.	A series of short, structured workshops is recommended with the goal of each workshop to produce supplemental materials and train in innovative presentation techniques.  For example, participants could create as part of such a workshop simple traveling displays and short, eye-catching, one page descriptions of CBNRM options in Setswana (and English where appropriate) to be used by district level Conservation Education officers, NGOs and CBOs.  It will be important to include a training of trainers component so that the extension team is able to continue training new groups.  There are excellent NGO facilitators in country who could be used as resource persons during such a series of workshops.  Outside technical support will probably be needed on production methods.

6.	A mechanism for fast, efficient, consistent communication flow for up-to-date information to the districts such as a one page FYI memo should be designed and implemented.

7.	Regular, consistent follow-up after initial workshops is critical to generating multiplier effect, maintaining momentum, providing motivational support and technical assistance as needed. This can be as simple as a brief phone call or letter one or two weeks after the workshop, face-to-face meetings, small group meetings, faxes, newsletters, or attendance at another function as a resource person.  This follow-up support helps the participates to localize and apply the information.  The purpose is to avoid two of the well-known classic pitfalls of workshop training events: 1) no application of the materials afterwards to the real world situation and 2) initial application thwarted by barriers encountered which results in negative reinforcement and then the participant is unlikely to try again.

8.	It will be important to relate follow-up activities to the recommended actions that participants have listed as part of the wildlife policy workshops. Record-keeping is critical, but can be simplified using a standardized form which can be periodically reviewed to evaluate the impact of the extension efforts and spin-off activities.  The monitoring and evaluation component of NRMP could assist in developing a simple follow-up strategy to monitor and record results.  Time given for writing must be part of the process.

9. 	Continue cosponsoring events at the district level and expand participation in the events of other agencies (NGOs/CBO, teacher training).  This expands the impact of efforts at a minimum of cost while at the same time increasing sustainability by increasing networking.

10. 	Continue materials development in Setswana whenever possible, for displays, simple brochures, and expand topics to include veld products, relation with agricultural policy and the range of CBNRM options.  Localize information to suit the needs of the target audience and speed actual implementation on the ground (gazettements, management plans, maps with boundaries, quotas).

Reprint a large number of selected posters using a smaller, non-laminated, less-costly production method in order to have broader coverage.  Posters should be prominently displayed in as many places as possible including DWNP Headquarters, every district office, every active educational center, every active environmental education or conservation-oriented NGO should have a set of posters and/or display. Every game scout leaving BWTI should have a set of materials to use. Game scouts and other senior DWNP staff already attend and participate in a wide number of capacity-building workshops done by IRCE, NGOs and CBOs.  Conservation education materials should be used whenever possible at these events.

.	11	Continue the production of the CBNRM video as rapidly as possible and put into immediate use.

12 	Maximize publicity to build awareness in the general public by expanding the multiplier effect and networking potential of key target audiences.  Strategically use available resources by broadening the variety of activities to include shorter, less-expensive, less time-demanding forum than only three day workshops.  Explore the use of media channels for press releases, radio, TV, video, newspapers.  Again, being selective by emphasizing those media that result in a minimum of staff effort for a maximum of publicity to reach the target audience.

4.0 	Impacts of the Natural Resource Management Project

4.1	Community Empowerment

Under the NRMP, a new relationship between communities and the GOB has developed.  In this partnership, communities and the GOB share benefits and responsibilities.  In the normal relationship, the GOB plays the role of the benefactor and communities are the beneficiaries.  This has been positive in the sense that the GOB has provided basic needs such as water and schools for many communities.  But, it has also meant that the GOB is the leader in ideas and initiatives.  Under the new partnership, the community has less dependence on the State but a much greater chance to set its own priorities and more opportunities to achieve those priorities.  The wildlife and veld enterprises are ideal vehicles around which to form these new partnerships.  These enterprises have real meaning and consequences to people.  In these cases, the idea of greater responsibility is linked to the actual production of greater revenues and other benefits.

Important Changes Over the Last

Five Years

1.	Suspicion has been changed to cautious confidence.  Communities did not trust DWNP in beginning. Now, communities solicit the advice and counsel of DWNP personnel.

2.	Incipient partnerships have been formed between communities and the GOB and between the communities and the private sector.

3.Some District Officials feel that the NRMP provides  services that he can provide to commonties.  These include the Problem Animal Control and training on more effective management of natural resources.

An integral part of the new relationship is trust and confidence between the GOB and communities.  One indicator that this is happening in the Trusts developed  under the NRMP is the change in attitude by the communities to DWNP personnel.  Prior to the NRMP, DWNP were not welcome in most communities because of their repressive behavior in dealing with wildlife issues.  Today, communities solicit the assistance of DWNP agents in managing wildlife, in helping the enterprises, and dealing with problem animals.  Mistrust and suspicion has been replaced by confidence and collaboration.

The approach developed under the NRMP supports the GOB National Development Plan 8   which will move the whole country to a new partnership relationship by giving priority to communities which take initiatives.  The GOB is coming to the same conclusion as those implementing NRMP:  shared responsibilities and benefits are more effective in achieving objectives than a benefactor/beneficiary relationship.

While the benefits to the new relationship seem to be obvious, there is also the tendency of communities to wish to maintain a certain dependency on the GOB.  It is less risky and there seems to be a flow of benefits.  And, on the GOB side (just as in other governments in the subregion), there are those who would tend not devolve authority.  While progress has been achieved, a critical phase is upon the project.  If tangible benefits continue to be produced from the new partnership, others in communities and the GOB will more likely be convinced that the partnership is right.  If those benefits are far less than expected, then the concept will be in deep trouble.

One of the NRMP counterparts is much more optimistic for the future of Ngamiland area.  There is a broader base of options for people in rural communities to pursue their livelihoods, people have more authority and more options and skills to exercise that authority.  He sees more cases of people trying new things.  It appears that people no longer see themselves as hostages to a confined set of circumstances.

In the development of the partnership between the CECT and the District Government, the communities through representation on the CECT have greater responsibility to negotiate and advocate than before.  This responsibility is being exercised.  This was illustrated during the development of the partnership between CECT and the district government and the negotiations between the communities and the Safari operator.  The CBO is a better partner when it can negotiate effectively.  NRMP facilitates this process, e.g., with the Safari operator and with the Forestry Service.

One can not escape the importance of cattle to social status and the resulting patron client relationships which result.  These relationships form the backdrop against which any CBO is formed and may well form the background against which joint ventures are negotiated .  The fact that trusts are working even through they include individuals with different often competing  vested interests, ethnic groups, religious affiliations and so forth; that communities who have never worked together before are beginning to function as units; and that for the first time communities are beginning to set their agenda rather than respond to an agenda set by the government or a donor may well begin to break through these older lines of patronage and pave the way for more equitable societal interactions in the future.

People are now exercising choices which a) may not have existed 5 years ago and/or b) they may not have had the authority to exercise.  In exercising these choices, a number of issues are coming up which may not have come up before, for examples: elections of representative boards count, skills count, people are no longer hostage to a single source of livelihood or to a particular body of people; members of positions of authority in the Trust work for members of the Trust and are accountable to the Trust members.

4.2	Policy and Institutional Impacts

Within the DWNP, there has been a  role reversal from a policing, enforcement institution to an extension institution.  As a result, there has been impact on the institutional structure with the addition of the community extension division.  Empowered communities have started a demand pull situation on policy formulation with DWNP that wasn’t there before, and the department has to respond to the demand.  CBNRM also causes creation of new, stronger institutions - communities are nascent institutions that are becoming more representational and accountable with the people and their own resources.  These impacts are also felt in a wider institutional perspective, within MLGLH, MFDP, and these impacts cross borders.

Broad  impact

Some government officials see the CECT demonstrating that the rural economy can be diversified, which is a goal of the National Development Plan 7.  They would like to see the rural economy be less dependent upon livestock and GOB programs and see the multiplication of activities of the CECT and Village Trust Committees as models for other communities.  This economic diversification by CECT and the Village Trust Committees is new.

There is also a change in perception that policy change requires a process in which various stakeholders engage in reflections and discussions versus a one-off exercise conducted by a team of experts.

Again, there are changing relations between communities and the GOB.  Up to now GOB has provided many resources to communities and communities have come to depend upon the GOB, sometimes to the detriment of developing their own initiatives.  Under the National Development Plan 8, the GOB intends to begin to reduce support to communities and move to a partnership within which the communities with most initiative would be favored. The CBO’s developed under the NRMP are examples of communities mobilizing resources.

Unexpected outcome of NRMP is that districts have more ways to respond to requests of communities.  In particular, Problem Animal Control was mentioned and extension on wildlife management as two requests for which they can better respond.

4.3	Economic impacts

“The new regional economy in Southern Africa fundamentally alters the potential returns on Botswana’s stock of natural capital. High value commercial uses (both consumptive and non-consumptive) offer real alternatives to subsistence, and low value uses. Therefore, the best economic strategy for rural Botswana is a regionally-oriented strategy which capitalizes on Botswana’s comparative advantages in that market.”(Shaikh, 1996)

There is an opportunity cost for a shift from subsistence use to marketing of the resource base at a sustainable pace. The rural populations must give up their traditional life style as subsistence and market use can not occur with the same resources. The cattle interests must give up a very lucrative activity where benefits go to very few for an activity where the benefits are widely shared. The policy makers must shift from giving concessions to the moneyed interests to acting for the population in opposition to the moneyed interests.

If the resource base is managed and not destroyed, the long term potential for earning foreign exchange, maintaining a high GDP, and increasing rural income and employment, and serving the majority of the people of Botswana, lies within the Hotel and Wildlife sectors and associated rural enterprise development as demonstrated by the activities of the Natural Resources Management Project.

The evaluation team conducted a detailed economic analysis on the rate of return for the project under three scenarios: 1) project closure at current PACD; 2) closure after a two year extension, and; 3) continuation of project activities for five years.  The complete analysis is found in annex 2, however, some of the salient points follow.

If the project were to close at the present PACD, only Chobe and Sankuyo would survive as a wildlife activity. Kuru Development Trust work on cochineal would continue as they have some sustainability, are not completely dependent on USAID funds and they are well on the way to market. All other activities would collapse and poison the wells for any other donor to do follow on. For this scenario the costs and benefits of Chobe and Kuru Development Trust were continued and all else written off.

The benefits off the two year extension case were flat lined at present levels for Chobe and up to estimated production levels for those in startup, after which they were also flat lined. The two year extension case would allow no new activity, but should allow sub-projects now in the gate to at least get started.

A five year extension, or phase 2, or new activity rooted in the solid base of community work of NRMP, would allow the spread effect to kick in and increase the return to the investment already expended.  In this case activities are replicated until year 2002 at which point all the relatively easy community projects would be in place. and all community wildlife management projects would be in place.  The cochineal sub-project was not replicated as this type of very high value niche is limited.  The other activities were used as illustrative of the type of returns that could be expected from further activity.

|  | Millions US Dollars |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Options | Investment | Additional Investment | Return | Internal rate of return | Benefit cost ratio |
| end project | $19.89 |  | $50.39 | 5.60% | 2.5 |
|  |  | $4.79 |  |  |  |
| two year extension | $24.68 |  | $70.98 | 6.90% | 2.9 |
|  |  | $5.54 |  |  |  |
| 5 year extension | $30.22 |  | $167.08 | 10.34% | 5.5 |

Table___ Community benefits only, no secondary benefits, no indirect benefits, no district government benefits, no individual benefits, no reinvestment benefits.

The internal rates of return of the analysis are seen in table___ . The two year and the five year cases are more than acceptable for a private sector venture considering the conservatism of the analysis.  Considering that it is a bilateral aid project housed in a government agency, it is astounding.  However, the two year case is still picking the fruit before it is ripe.

Over the economic time frame, project investment in community resource management capacity will have economic and financial benefits far exceeding break-even for the investment made by USAID and other donors. In addition this capacity may be used in other non-resource based sectors of the economy and the society to further advance rural people. From the view point of benefits to rural poor the extension of five years makes the most sense. From the point of view of consolidation of investment and economic efficiency a five year extension makes the most sense.  From the point of view of balance of payments, and  economic stability a five year extension is the best choice.

4.4     Environmental Impacts

Better management through detailed management plans will lead to better protection of the natural areas, especially if followed up with appropriate training  provided by the EU.

Broad Impact

In 1992, Chobe District and community counselors were skeptical of the community approach of DWNP but supported the idea of a community-based approach.  The NRMP helped to give confidence to try it  In the beginning, the idea was challenged by some hunters because they feared losing hunting rights with subsequent effects on their livelihoods.  When the community received its first check from its partnership, they eventually gave up the resistance, and some have become Board members.  Several people who are strong supporters of the CECT admitted to being ex-poachers as well as hunters.

Sustainable use or environmental impact assessments for all non wildlife utilization projects have not been done.  These must by done so that appropriate harvesting, sustainable use, conservation measures can be known, understood and incorporated into project design

In both Gweta and Sankuyo the communities indicated that there had been a decline in poaching as a result of their management of their own wildlife quota.  They no longer go out and hunt because they get 50% of the meat and in Sankuyo and they also kept part of the quota for themselves to hunt (non-trophy animals).

Safari companies are becoming major players in anti-poaching activities.  Last year in Chobe, the four reports to which the Botswana Defense Force responded to came from Safari operators.

4.5	Regional Impacts

The project is inherently regional in nature from economic point of view.  Developing high value products for trade with South Africa and the international market, but done on the terms of Botswana enterprises.  The entire gamut of project activities including veld products, wildlife harvesting, and tourism, produce returns from across national borders. All of these products and services are exported.  Tourism is an export sector. Veld products markets including carmine dye, Marula fruit products, bottled water for tourists, and even Mopane caterpillars, are across borders and produce foreign exchange.   Probably less than 10% of project economic benefits are local origin. With this in mind, one of the major areas that RCSA could address is assistance in organization of the regional tourism industry. Regional solidarity and pooling of marketing in regional tourism circuits would do much more for the economies of Southern African states than many so called development activities.

If a regional approach focusses on international agreements on coming to terms on managing those resources which cross boundaries (e.g., water, wildlife, fisheries, watersheds, etc.) then it makes sense to include processes to ensure better management on each side of the border.  In the Chobe area, for example, some wildlife may spend part of a year in Namibia, Zambia, or Zimbabwe as well two or three countries during the course of a year.  It does no good to have good management practices in one country and poor practices in the other.  Sound sub-regional policy agreements achieved amongst governments will be marginalized if management practices on the ground are not improved.

Broad Impact

A District Councilor in Chobe feels that the CBO approach has given him a topic which is shared by his counterparts in Zimbabwe.  Since the two government systems are different, he has had problems finding common ground on which to relate to his colleagues.  However, since both Zimbabwe and Botswana are working with community-based wildlife, they can exchange experiences to the benefit of both.  The DC thinks that the same would apply to his colleagues in Namibia, Zambia, Malawi, Lesotho, etc.  Empowerment of communities would be a common theme in these discussions.

As the CBO approach as being developed in Botswana has promise for being a viable option for managing veld, wildlife, water, fishery and watershed resources, then the lessons from the NRMP should be shared by communities and governments throughout the subregion.  In supporting the development of an approach which maximizes the sharing of ideas and experiences, we recommend that the Regional Program build on the current NRMP activities to include government, community, and NGO members in neighboring areas.  For example, the CBO approach is advanced in the Chobe area.  The CBO is in the third agreement with a private operator in managing a NRM-based enterprise and is dealing with more complex issues.  The District government has extensive experience in setting up an enabling condition to provide incentives for the CBO activities.  And, the private operator has important experience in dealing with CBOs.  But, all three parties say that there is still a ways to go before the CBO will be capable of dealing with the enterprise on its own and lessons remain to be learned on the side of the District government and private operator.  In several respects, now is the critical time.  Critical issues have been raised, which if successfully addressed will move all  three parties onto the high part of the learning curve and which will form the foundation for CBO-government-private sector partnerships in the subregion.  The relevance of these lessons on partnerships are not limited to wildlife management.

In addition to finishing the development of a viable model for CBO-government-private sector models, continued assistance to communities like Chobe could be implemented on a sub-regional basis.  For example, Namibian communities bordering the area managed by the CECT are interested in the experiences of the CECT.  The same may be the same for communities in Zimbabwe and Zambia.  While not compromising support to the CECT which will carry it to the point of being a viable and independent organization, a multinational team could be formed in the four-country area around Chobe that would include representatives from the communities, governments, NGOs, and private sector in all four countries.  The TA team supported by the RCSA would be stationed in Chobe, but would facilitate exchange of information and experiences across borders.  Regular exchanges of information and ideas would be made on a regular basis.

4.6	Impacts on Small and Medium Enterprises

The project is based on the creation of small enterprise based in local communities run by a board of directors and answerable to shareholders. The enterprises are all natural resource based and include, wildlife hunting, wildlife tourism, scenic tourism, cultural tourism, gathering processing and marketing of mopane caterpillars, marula fruit, and grapple. The domestication of grapple, and cochineal, and the bottling of mineral water are also among the activities. There are several other opportunities waiting to be tapped. Several secondary enterprises are being financed from the earnings of these primary activities. They include at this early date, a petrol station, a forest salvage operation, and several other opportunities.

Each of these activities create other activities such as craft sales, jobs as guides and waiters, and management positions. Secondary products are produced such as marula oil, briquettes, cattle feed from opuntia and phane. Growing of opuntia increases the growing of vegetables for home consumption. Markets also open for locally grown vegetables to serve the tourism market. It is difficult to find a sector of this project that does not have some effect on small and medium enterprise development.  Project advisors are constantly involved from the policy aspect to community organization, social aspects of production, the marketing of the end product, and the strengthening of small businesses capacity to make management decisions and distribute the earnings in an equitable manner.

4.7	Gender

The majority of Botswana’s rural population has steadily lost access to key productive resources.  Within this group women have suffered particularly.  The majority of veld resources users are women with the exception of timber. CBNRM provides an opportunity to utilize resources that have not been appropriated by the wealthy to the poor majority.  The institutional structures that ensure accountability and representativeness empower rural women by giving them a voice in decision-making heretofore denied them.  The impacts of this will be seen in a more equitable division of wealth and labor by gender over time.

One can make a similar argument for disadvantaged ethnic groups, people who have lost access to cattle to recession, cultivation land, which of course also include women.

Batswana Women in communities appear to be respected and empowered though they may not be equally represented in the political arena they do take leadership positions on village committees and are the prime beneficiaries of most veld product enterprises.  They also benefit as community members from the jobs, meat and income provided through wildlife utilization joint ventures.  Furthermore they are equal partners in training activities, exchange visits and such like.

Despite the apparent inclusion of women in decision making,  NRMP needs to ensure that as enterprises are developed women continue to remain in a driving seat and that they are not disempowered or disinherited as veld products which have always been considered women's goods are commercialized.  NRMP also needs to understand what incentives women require to participate more fully in the economic enterprises being proposed.  Finally NRMP should encourage the greater involvement of women in the various government departments in the project - the civil service appears to have less gender balance which results in more of the Government advisors seem in villages being men - civil service women also need to provide role models in the village setting.

5.0	Project Management Issues

5.1	Contractor Performance

The main contractor for the NRMP is Chemonics International.  It has two sub-contractors Domestic Technologies Incorporated (DTI) and Conservation International (CI) which provide some of the long term advisors.  DTI provides advisors for problem animal control/NRM, resource economist and BWTI trainers, CI provides the Community Extension Advisor.  USAID also has cooperative agreement with PACT whose activities fall under the overall Botswana component of the NRMP.

In general the performance of the contractor has been exemplary.  The project has consistently documented it’s progress and constraints encountered.  The constant analysis of current problems and open discussions on potential solutions is evidenced in the amount of team work involved in the project.  The professionalism and expertise of project staff has been a consistent, glowing observation by all partners and stakeholders interviewed.    In addition to competently conducting their tasks as per their scope of work, each project member engages in a wide variety of activities which go beyond their scope.  This willingness to be flexible and respond to opportunities has been instrumental in producing the results of this project to date.

The evaluation team was continually impressed by the amount of leveraging the project has done to produce more than their budget allowed.  NRMP deserves to be recognized that the team did not just go for points, but consistently strove to have input and a voice for CBNRM whenever the opportunity arised, even if they didn’t get full credit for it. As part of its assistance the NRMP provided economic analysis and a survey on the potential of the forest  (A mill operated up to 1993).  As further assistance to the CECT and Forestry Service, NRMP helped conduct a market survey for wood that would be salvaged.  This survey showed a good potential for wood and wood products and is indicative of the broad range of assistance being provided by the various advisors.

IRCE has made an exemplary effort during a quick start-up phase to initiate capacity-building exercises and develop a grants management mechanism.  This start-up phase was positively affected by the highly competent and professional Batswana staff recruited by PACT.

However, there a competitive atmosphere appears to exist between NRMP and IRCE that works at cross-purposes to the common agenda of both agencies.  Both chief of parties are working hard on this relationship but it may be time for the USAID project manager to step in to promote more effective team building and a greater degree of information sharing and collaboration.  IRCE should not see itself in competition with NRMP advisors nor should either component see themselves as having all or even the right answers.  Similarly,  NRMP and USAID should not see IRCE as a funding body.

The evaluation team felt that the management process (meeting, review of proposals) was in place but obviously not working effectively.  The apparent tension between NRMP and IRCE should have been resolved during the project’s frequent meetings.  The project manager needs to take a more assertive role in ensuring team cohesiveness.

To decrease the amount of confusion over IRCEs intentions, it would be better to separate financially and materially resources given towards building NGO capacity and those dealing directly with CBO capacity-building.  In this context, the evaluation team recommends that  IRCE divides itself administratively into three components.  The first, grants management will be only managing the grants according to the oversight of the Proposal Review Committee.  The second, NGO capacity building should deal only with that aspect of the project.  Finally the third would deal uniquely with the community capacity building aspects.  Resources should be divided to the two capacity building components - three quarters to CBOs and one quarter to NGOs.

It should also be noted that IRCE, while taking the lead under NRMP in organizational capacity-building,  are being supported in this effort by the Chemonics and sub-contractor staff.   In particular NRMP staff had majority input on the CECT proposal, Kalahari Conservation Society,  Sankuyo and Gweta communities. Coordination of project efforts within communities is essential so that separate components are not pulling villages in different directions, training opportunities or time demands.    The fact that this work is being undertaken in less than optimal team conditions may have given rise to the feeling in Chobe that there is a disjunction between the advice given by different advisors and different components of NRMP.

5.2	USAID/RCSA Performance

The success of NRMP lies in it’s approach towards community-based natural resource management.  Put briefly it is to 1) work at the pace of community, present them with opportunities and let them decide what and how to do things; and 2) not use financial or material resources as a way to leverage action from the communities.  The first necessarily take a long time to nurture and the NRMP excelled in the patience and gentle guiding to assist the communities to organize and decide among themselves what they wanted to do.  The second point was probably the more difficult for the project to adhere to because of the often real, or imagined, emphasis AID may place on “getting the money spent”.  That the RCSA did not exert this type of pressure is just one example where the Mission deserves recognition for responding to realities of community development.

USAID management and support from the project manager has been much appreciated by project staff and government partners.  The project manager is regarded as being well informed and facilitative. The project manager makes site visit on average once per month.  He has been to several sites more than a couple of times.

However, some areas that may need improvement have been noted by the evaluation team:

1.	Greater leadership and facilitation role to unite the team.  Regardless of regular AID/ project staff meetings (usually on a weekly basis) there could be more cohesiveness  in team approaches to CBNRM, especially between IRCE and the rest of NRMP staff.  In this context, the project manager needs to take a more assertive role in ensuring communication and coordination of all project components.

2.	RCSA management needs to become more fully aware of project developments in the field as they have significant impacts on other strategic objectives (Democracy and Governance and Small, Medium Enterprises).  This will provide insight for management to improve linkages between the strategic objectives.

3.	The RCSA and Strategic Objective team leader’s failure to communicate their concerns creates an apparent lack of interest and communication with project staff.  This atmosphere makes project staff question the degree their opinions are considered and may lead to demoralization.   As an example, the evaluation team witnessed a meeting between NRMP staff and the Strategic Objective team leader in Maun.  The NRMP staff felt it was constructive however the Strategic Objective team leader felt the exact opposite.  This makes the team question how much listening is done on both sides.

4.	This apparent lack of support has raised substantial concerns among government officials and other donors.  They fear that if the project is not supported in the future it will “muddy the waters” for all future CBNRM activities in the future.

5.	USAID must provide clear guidance on what data it expects the project to collect to feed into its own reporting procedures. It is recommended that the project manager and project staff develop, and agree upon, appropriate data requirements to determine progress towards results.  The Fiebig report should form the basis of these discussions as well as the socioeconomic studies already conducted under the project.

5.3	Partner Participation

5.3.1	Department of Wildlife and National Parks

As this report documents,  DWNP is in the process of implementing one of the most successful natural resource management projects in Africa.  It is also implementing the largest effort to diversify the rural economy. However, the department has internal structural problems that preclude it from expanding more effectively towards implementing community-based natural resource management. Staff shortage and the fact that potential counterparts have been sent on long-term training programs have made DWNP’s involvement in ensuring long-term sustainability of the project sporadic.

To solidify gains and progress to date, more governmental support needs to be given to DWNP to strengthen its staffing at headquarters and in the district.  The lack of counterparts to the advisors has been the single most detriment to sustainability of some of the community activities.

NRMP has never been fully integrated into the department, although all consider that this has improved substantially within the last year. The department is actively involved in the annual NRMP work plan exercise.

DWNP is moving from the old, classical enforcement park management organization to one recognizing importance of including communities as partners in conservation.  This is difficult, time-consuming transformation to take place,- considering it has to maintain a law enforcement function also.

5.3.2	Non-government organizations

As discussed earlier, NGOs were seen as key players in the original project design but had limited involvement during the period preceding the mid-term evaluation. There is now increased engagement of NGOs in community resource management and a promise for specific, service delivery support roles for NGOs in CBNRM.  There is also potential for increased NGO participation in advocacy.

5.3.3	Other partners

Donor Collaboration

The evaluation team has been impressed by the amount of leveraging of other support and resources the project.  This leverage of outside resources, both in manpower and financial resources have led to increased impact of the project outside of their main activities.  Examples of leveraged activities include:

The EEC is planning support to the CECT salvage operation in the form of equipment and training.  Under the current plan being considered, saws, extraction equipment, and training will be provided by EEC.  This is another example of where support by NRMP has levered support from another donor.

Other examples include SNV, ODA, IFAD and DANCED activities. All have drawn heavily on NRMP documentation.  SNV mentioned that they are involved in CBNRM directly because of NRMP.

Local governments have played an increasing role in CBNRM with the assistance of the NRMP.  Because of DWNPs decentralized to district levels, they are now the entry point to ensuring the longevity of the community trusts.

6.0	Financial Implications of Evaluation Recommendation	..

The following table indicates illustrative costs for a two-year extension.  These costs do not include costs that will be incurred for a re-design of the project for a follow-on period, residual funds at the end of the current PACD, nor do they indicate counterpart funds from the Government of Botswana.

Table x: Illustrative Costs for a Two Year Extension

| Admin Costs | 1997/98 | 1998/99 | TOTAL |
| --- | --- | --- | --- |
| Admin. Ofer. (Contractor) | 63,000 | 66,150 | 129,150 |
| Asst. Admin. Ofcrs. (Contractor) | 153,000 | 160,650 | 313,650 |
| Admin. Ofcr. (Cooperative Agreement) | 30,000 | 31,500 | 61,500 |
| Asst. Admin. Ofcrs, (Cooperative Agreement) | 42,000 | 44,100 | 86,100 |
| CBO Support |  |  |  |
| LTTA (4 ex pat) | 360,000 | 378,000 | 738,000 |
| LTTA (3 local hire) | 132,000 | 138,600 | 270,600 |
| STTA | 100,000 | 500,000 | 600,000 |
| Grants | 500,000 | 250,000 | 750,000 |
| Capacity building to communities | 80,000 | 40,000 | 120,000 |
| Personnel Planning and Training |  |  |  |
| LTTA (HRDU) | 135,000 | 0 | 135,000 |
| LTTA (BWTI) | 315,000 | 330,750 | 645,750 |
| STTA | 75,000 | 50,000 | 125,000 |
| Short term training | 75,000 | 25,000 | 100,000 |
| Policy |  |  |  |
| LTTA (COP) | 135,000 | 141,750 | 276,750 |
| STTA | 175,000 | 75,000 | 250,000 |
| Workshops | 75,000 | 25,000 | 100,000 |
| NGO Capacity |  |  |  |
| LTTA | 81,000 | 85,050 | 166,050 |
| Workshops/Capacity | 75,000 | 25,000 | 100,000 |
| STTA | 25,000 | 25,000 | 50,000 |
| Planning & Applied Research |  |  |  |
| LTTA | 117,000 | 122,850 | 239,850 |
| STTA | 100,000 | 50,000 | 150,000 |
| Environmental Education |  |  |  |
| LTTA | 72,000 | 75,600 | 147,600 |
| Workshops/Materials | 100,000 | 50,000 | 150,000 |
| Project Operations | 125,000 | 131,250 | 256,250 |
| Contract Team Support |  |  |  |
| Vehicle operations | 75,000 | 25,000 | 100,000 |
| Commodities | 50,000 | 25,000 | 75,000 |
| TOTALS | 3,265,000 | 2,871,250 | 6,136,250 |

7.0	Post evaluation considerations and action recommendations

1.	Considering NRMPs excellent progress to date and substantial contributions to the regional strategic objectives, the evaluation team feels strongly AID should consider a long term commitment (5 years or more) to community-based activities.   This will capitalize on the investment by GOB and USAID.

2.	In this context, it is recommended that the project continues with minor adjustment for two additional years, during which a new design for a follow on activity based on community actions should be completed.  Current capacity-building activities will allow for follow on activities in other sectors and should be taken advantage of.  The value added to existing project activities given an extension are outlined in annex 1.

3.	There should be a shift in responsibilities for implementation of activities from the NRMP advisors to their counterparts and other DWNP staff as soon as possible.  This requires DWNP to appoint appropriate, qualified counterparts and to budget appropriately.

4.	During the two year extension greater emphasis should be given to capacity-building at the district level for CBNRM.  To fully accomplish this DWNP should hire additional staff to fill the district community liaison positions and NRMP management should consider opportunities to ease logistical constraints i.e housing closer to the communities.

5.	The NRMP main contractor should provide overall monitoring of CBNRM replication and spin off  activities within the project since they have a broader perspective and a wider range of technical staff. USAID needs to develop a memorandum of understanding to the above effect

8.0	Lessons Learned

The following specific lessons distilled from this evaluation of the NRMP seem to be relevant:

1.	Project planners must acknowledge that community capacity-building should foster responsibility and not just participation.  This is a time consuming process that normally goes beyond the typical project life span.

2.  	Organizational capacity of  community groups must be addressed as early on as possible.  Again, this is a time consuming process and the earlier communities gain organizational skills the sooner they will be able to take over responsibility.

3.	Although processes may differ in different countries, effective community-based natural resource management requires action at the national, district and local level.  Therefore, all three levels need to be working with a common goal.

4.	Demonstration projects in Botswana illustrate that approaches for CBNRM must be localized.  For example,  communities may work with local government, NGOS, private sector or on their own depending on local circumstances.

5.	Distribution of funds should not exceed the communities absorptive capacity to manage them, nor should they negate the responsibility of the community for their own actions.

6.	Empowerment Works.  People in Chobe, Gweta, Sankuyo and Xai Xai are making choices about enterprises, about leaders, about relations with the GOB and private sector that they were not making five years ago.  They see that their decisions make a difference in community income and that they have a say in the decision.  Instead of being indifferent to the leadership of the Trusts or Quota Committee, Trust members are getting involved in selecting Board members and in challenging the leadership.

Annex 1:  Value Added and Constraints to Project Componets with an Extended PACD

Personnel Planning and Training

-DWNP will have developed a personnel planning and training program

-Increased effectiveness of the DWNP extension service that has the tools and commitment to work in support of CBNRM

-Increased training for district officers in CBNRM initiatives

-Creation of adequately staffed and trained sociology office as part of an adequately staffed and trained community extension unit

-BWTI directly addressing vocational skills of DWNP staff

Constraints:

-Civil Service regulations that prevent DWNP from hiring staff, buying vehicles, decentralizing budgets need to be reformed so political will, when it exists, is not undermined by bureaucracy

-Need a strong commitment on the part of BWTI  to carry through standards of training and discipline

Policy and Institutional Development

-CBNRM policy will have been vetted, adapted, approved and implementation started

-Additional CBNRM guidelines will have formulated (i.e. Trust formation, district institutional guidelines for CBNRM, benefit distribution, accountability)

-Development of a strong CBO network capable of articulating interest and initiating action

-Creation of policy which transforms current open access resource regimes to a common property, community managed regime

-Increased CBO/NGO participation in national policy areas

-Policies will be adopted and not just in discussion stage

-Policies will become more broadly understood

Constraints

-Policies can be produced but will not be implemented without commitment

-Inadequate extension capacity of institutions at community level to manage resources

-Lack of a public awareness/relation outreach forum

CBNRM - Wildlife and Veld Resources

-If DWNP/NRMP succeeds in bringing ownership to open access resources (all veld), CBNRM raises the intrinsic value to users.This added value can translate into improved incomes for marginal, impoverished people and improved mgt practice

-A number of communities will have the capacity to deal with their own problem animal control problems, thereby alleviating a hard pressed DWNP

-Community Escort Guides will have received training in NRM monitoring to achieve sustainable offtakes

-Communities will become more sensitized on issues relating to conservation and sustainable utilization

-continued, and strengthened economic diversification in rural areas

-Increased number of projects, increased number/range of resources utilized, increased spinoff activities from main activities, increased integrated planning

-Veld products - an increase in the range of veld products being processed at community level and new markets for such products. The sustainability issues addressed and improved mange

-WMAs - all WMA gazetted and under some form of community management in collaboration with the private sector and districts

-All community CHAs will have local institutions and coherent program strategies in 5 years.  District facilitation capacity must therefore be developed in two years

-Skill for management of other forms of economic activity/projects would be acquired (i.e skills provided which could be utilized elsewhere in the rural economy)

-Increased economic and social equity, more democratic society as a result of these resources being controlled by people excluded from access to other resources

-Continued support to DWNP for wildlife utilization activities - reach the same point with veld resources that we have reached with wildlife

-Veld demonstration projects running with hands-on experience and environmental repercussions of CBNRM assessed

Constraints:

-Lack of regulations for WMAs and gazettement in some areas. Rights of those outside WMA not specified

-Counterparts not permanetly assigned or appropriately appointed

-continuing program - communication strategy on rights, roles and responsibilities for CBNRM

PLANNING AND RESEARCH (M&E)

-Better understanding of the socioeconomic processes that shape how people use resources

-Capacity of DWNP and other institutions with a role to play in CBNRM to generate and use socioeconomic info for CBNRM planning and implementation

-Solid research and data collection of a wider number of projects/activities that could shed light about what works best and could/should be emphasized in other projects

-Through expansion/institutionalization of OCAT increased CBO/NGO capacity

-Define the terms and conditions required for DWNP to understand and foster M&E as a key tool in management

-M&E institutions now being developed in DWNP should be integrated within a new CBNRM research unit of NIR -Nat’l Inst. For Research and Documentation -UB)(not taken out of DWNP but integrated in NIR) together with researchers from the research units at MLGLH, MOA, to facilitate and integrate research on all natural resource use, and provide a linking and capacity building forum.

Constraints

-Where based? Currently 1 person in DWNP wit- no authority. What forum is appropriate?

-Management must see information as a tool not a threat

-EIA - legislation and how M&E is linked

CBO/NGO Development

-Governance (Board training), management practices, financial management, leadership skills, community facilitation skills, technical advise on a consistent basis from stakeholders DWNP/NRMP/IRCE enhanced.

-CBOs would have been in existence for a long enough period of time to resolve organizational conflicts and to establish an approach that “works”

-A vibrant CBO network giving them a united approach and political clout. This cannot be done in two years -it might be possible in 5 years.

-NGOs- key role as neutral coordinating agencies(watch dog role) between community and venture partners should already be brought into process

-Expanded number of CBOs/NGOs working toward CBNRM and community empowerment through provision of capacity building support, skills transfer and advocacy.

-Small group of NGOs capable of facilitating CBO strengthening

-Increased policy formulation and implementation initiated by CBO network or CBOs individually - product of the institutional development referred to under that section.

-Develop an organizational development plan coming up with deliberate intervention plans for existing NGOs, have effective NGOs and this could be achieved through the OCAT also for CBOs

Constraints

-how to make it Botswana driven?

-How to get service to CBOs?- combination of services-

-gov’t limitations/civil service

-NGO limitations/conflict as  gatekeeper

-formation of NGO that respond to real constituency base -could provide services

ENVIRONMENTAL EDUCATION

-Formal- institute programmes through agencies such as CDD-build on existing material

Wildlife clubs, etc. supported (possibly taken into the hands of Education Department)

-Non-formal- NCS potentially important role player in information dissemination and coordination of environment related extension

-DWNP Education Division to be encouraged to play greater role in public information efforts

-Must ensure that all players involved in CBNRM fully understand the rights, roles and responsibilities of each other

-Increased awareness regarding conservation and sustainable utilization and therefore, increased participation in conservation activities.

-Greater knowledge at a national level of environmental issues and awareness at community level of how local management practices contribute to conservation and sustainability

CONSTRAINTS

-DWNP provides resources to con ed division - more skilled people go to districts

-NCS (coordinating body) may be a better vehicle for communication effort (but will have greater requirements to do this then DWNP) - work through other agencies

REGIONAL

-Greater inter country project communication sharing experience and resources/markets and management /technical skill between CBOs in the region

-Demonstrated improvement in rural incomes and NRM - sustainability

-Greater efforts towards on the ground liaison between communities can bring about exchange of ideas or a technical level which will assist nrm projects.

-Extend regional impact by promoting exchange visits throughout region, at all institutional levels, (CBO, facilitator, gov) to share information.  For shared learning, CBO network, facilitator network and gov networks should be developed which operate extend regionally

-replication of national projects at regional level (with modifications) - networking (info sharing/exchange)

-Exchange allow accelerated progress - by avoiding mistakes - put pressure on laggers to do it right

-Grassroots capacity for nrm tied to larger processes responsible for labor & capital moving across borders

-Sharing of info and experience and therefore replicating those activities which are showing greater benefits

-Sharing some facilitators (for training) to benefit from economies of scale

-Through sharing experiences and lessons learned(networking) the whole of the NRM movement in SA is greater that the sum of its parts

CONSTRAINTS

-Define a development vision that allows AID to target aid regionally USAID must define this “artificial”

Annex 2: Macro and Micro Economic Analysis

ECONOMICS Macro

Botswana is fortunate to have received the services of two world renowned economists looking at the role and potential of natural resources in the national economy. The following section draws heavily from Shaikh, 1996 and Tyler, 1996. Unless specifically stated, all of this section is referenced to these two authors.

Godfrey Tyler looked at the role and potential based on the Social Accounting Matrix (SAM) which is a system for placing the costs and benefits of the various sectors of the national economy in a balanced account similar to the way a small firm uses double entry bookkeeping for it’s accounts. He used the SAM to construct a modeling framework called the Computable General Equilibrium Model. This allowed the observation of potential effects resulting from changes in assumptions. It is a big “what if”model.

Tyler ran a base case and  six simulations with this model as follows.

1. Increase beef export demand by P 14 million

2. Increase hotel services demand from visitors by P 14 million

3. Increase hunting demand from visitors by P 14 million

The complete effect of these three simulations on the base case for various sectors of the economy can be seen in Table___.

|  |  |  | Percentage Change from Base Solution |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Base | Extra Export Demand |  |  |  | Lower | (5) plus |
|  |  | Solution |  |  |  | (3) plus | beef | Expanded |
|  |  | Million P | Beef | Hotels | Hunting | shift | prices | (2)&(3) |
|  |  |  | (1) | (2) | (3) | (4) | (5) | (6) |
| 1 | Real GDP at factor cost | 8291.3 | 0.13 | 0.17 | 0.22 | 0.40 | -0.77 | 0.02 |
| 2 | Export Revenue | 3902.1 | 0.30 | 0.34 | 0.34 | 0.30 | -1.75 | -0.40 |
| 3 | Import Payments | 3444.4 | 0.21 | 0.17 | 0.10 | 0.52 | -1.21 | -0.66 |
| 4 | current account surplus | 480.5 | 0.65 | 0.96 | 1.20 | -0.67 | -3.73 | 0.54 |
| 5 | Net Indirect Taxes | 1057.4 | 0.22 | 0.15 | 0.08 | 0.31 | -1.25 | -0.78 |
| 6 | Income Taxes | 1356.3 | 0.11 | 0.19 | 0.26 | -0.15 | -0.64 | 0.26 |
| 7 | Government income | 5467.1 | 0.12 | 0.16 | 0.19 | -0.04 | -0.70 | 0.00 |
| 8 | Govt real consumption | 2596.0 | 0.03 | 0.16 | 0.19 | -0.13 | -0.15 | 0.11 |
| 9 | Government savings | 1731.0 | 0.12 | 0.16 | 0.19 | -0.03 | -0.70 | 0.00 |
| 10 | Cattle Output | 274.0 | 0.91 | 0.29 | 0.22 | 1.35 | -5.30 | -4.23 |
| 11 | Cattle value added | 262.1 | 0.92 | 0.31 | 0.19 | 1.37 | -5.27 | -4.24 |
| 12 | Cattle exports | 0.0 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| 13 | Agric, beef, other process output | 840.4 | 2.10 | 0.17 | 0.13 | 0.84 | -11.84 | -11.17 |
| 14 | Agric, beef, other process value added | 191.1 | 2.10 | 0.16 | 0.16 | 0.84 | -11.83 | -11.20 |
| 15 | Agric, beef, other process exports | 153.7 | 8.50 | -0.13 | -0.07 | -0.20 | -48.50 | -48.70 |
| 16 | Hunting gathering, output | 104.8 | 0.29 | 0.38 | 13.50 | 14.90 | -1.72 | 26.20 |
| 17 | Hunting gathering,value added | 99.0 | 0.30 | 0.40 | 13.60 | 14.90 | -1.72 | 26.30 |
| 19 | Hotels and restaurants, output | 178.2 | -0.17 | 8.00 | -0.06 | -0.12 | 0.84 | 16.50 |
| 20 | Hotels and restaurants, value added | 100.8 | -0.10 | 8.00 | -0.10 | -0.10 | 0.89 | 16.50 |
| 21 | Hotels and restaurants, exports | 147.3 | -0.14 | 9.80 | -0.14 | -0.27 | 0.88 | 19.90 |
| 22 | Employment, skilled | 745.2 | 0.24 | 0.38 | 0.12 | 0.35 | -1.34 | -0.46 |
| 23 | Employment, unskilled | 479.3 | 0.31 | 0.33 | 0.17 | 0.35 | -1.80 | -0.71 |
| 24 | Employment, informal sector | 549.5 | 0.76 | 0.29 | 0.73 | 7.90 | -4.40 | -2.35 |
| 25 | Profits | 3577.6 | 0.07 | 0.18 | 0.34 | -0.44 | -0.42 | 0.61 |
| 26 | Real Consumption rural waged households | 901.9 | 0.22 | 0.29 | 0.18 | 0.68 | -1.29 | -0.37 |
| 27 | Real Consumption rural other households | 758.5 | 0.33 | 0.25 | 0.29 | 2.77 | -1.93 | -0.92 |
| 18 | Hunting gathering, exports | 1.4 | 0.00 | 0.00 | 1100.00 | 1100.00 | 0.00 | 2100.00 |

Table from Tyler 1996. Line 18 was dropped to the bottom to facilitate graphing.

Fourteen million Pula is about 10% of the foreign exchange earnings of both the agriculture/beef/processing and the hotel sectors. The sectors involved only form a small part of the national economy thus the effects on other sectors and on the GDP are relatively small.  Hunting does the best by increasing the GDP  by 1.2%, followed by hotels. These two sectors also out preform agriculture/beef/processing in balance of payments, and budget surplus; has equal effects on skilled labor, and waged rural; has smaller benefits on unskilled labor.

Sector 18 was omitted as the magnitude of change is so large that other sectors can not be seen in the resulting scale of the graph.

4.Shift proportions of hunting value added from .2 informal .8 profit to .5 and .5.

This shifts some benefits from export hunting from commercial operators to local communities. This increases returns and employment  in the informal sector which grows by 7.9%. The hunting sector expands by 14.9%, cattle expands by 1.35% for local consumption, and agric/processing by .84% for the same reason. The overall effect is an expansion of the GDP by .4% the highest of any of the first four cases.  Imports also increase to meet rural household demand, canceling some of the foreign exchange advantage.

5. What is the effect of a 20% drop in beef prices.

This scenario is a possibility if market favoritism and subsidies were removed.  The GDP decreases by .77%, export revenue by 1.75%, and balance of payments drops by 3.7%. Other sectors also suffer.

6. Is it possible to compensate for a collapse of the beef market by shifting to wildlife and hotels?

Yes within three to four years.  With an increase of 28 million P in each of the two sectors. Real GDP, Government income and savings, restored, current account surplus larger than the base case.  The macro economic recovery requires expansion of hotel by 16.5% and the hunting sector by 26%.

Sector 18 was omitted as the magnitude of change is so large that other sectors can not be seen in the resulting scale of the graph.

Summary

“In many parts of rural Botswana the comparative advantage lies in marketing the rural resource base in ways which generate much higher levels of income than would subsistence use of the same resources. Wildlife and veldt products may still allow northern populations to eke out a subsistence living, at least until demographic pressures make it unsustainable. However, these same resources have a much higher value for tourism than for subsistence.” (Shaikh, 1996)

“The new regional economy in Southern Africa fundamentally alters the potential returns on Botswana’s stock of natural capital. High value commercial uses (both consumptive and non-consumptive) offer real alternatives to subsistence, and low value uses. Therefore, the best economic strategy for rural Botswana is a regionally-oriented strategy which capitalizes on Botswana’s comparative advantages in that market.”(Shaikh, 1996)

There is an opportunity cost for a shift from subsistence use to marketing of the resource base at a sustainable pace. The rural populations must give up their traditional life style as subsistence and market use can not occur with the same resources. The cattle interests must give up a very lucrative activity where benefits go to very few for an activity where the benefits are widely shared. The policy makers must shift from giving concessions to the moneyed interests to acting for the population in opposition to the moneyed interests.

Conclusions

If the resource base is managed and not destroyed, the long term potential for earning foreign exchange, maintaining a high GDP, and increasing rural income and employment, and serving the majority of the people of Botswana, lies within the Hotel and Wildlife sectors and associated rural enterprise development as demonstrated by the activities of the Natural Resources Management Project.

MICRO ECONOMIC ISSUES

What are the direct economic results of project activities to date, where are we on the economic time line, and what are the reasonable projections?

The economic time line of the project has little connection with the project time line. The short term vision of USAID administration requires looking at long term effects far beyond any PACD.  The usual time frame of economic analysis of around twenty years is also not sufficient when dealing with natural resources which, if the project is successful, may continue until society decides a different use of the resource base may be appropriate.  This nebulous future actually causes no discomfort in the analysis as future benefit fade into time as their present day values decrease through discounting.   There are schools of economic thought that support zero or negative discounting when dealing with unreplaceable bio-diversity or nonquantifiable esthetic values.  Both cases would apply in this analysis, however, the returns and the potential returns of the NRMP will suffice to economically justify continuation without a tally of the considerable nonquantifiable benefits.

The analysis of the data and estimates from annex____. takes an extreme conservative approach. The analysis is from the community’s point of view, that is, benefits accruing to government, private sector, NGOs, and individuals, in the form of jobs, fees, profit, or non community direct grants to NGOs, are not examined. Meat and craft sales are include as an estimate for STMT but not for CECT as data is not readily available from the project.  Supplemental benefits for KDT such as concurrent growing of opuntia and food, opuntia fruit, veld products sales, and opuntia livestock feed sales are not included.  None of the considerable amount of funds leveraged from other donors, private sector funding or NGO co-financing were included. None of the benefits were increased over time as might be the actual case from increased demand or better management

None of the cost or benefits of the Tswapong Mopane caterpillar subproject have been included as the stated goal is empowerment of women through increasing returns to the gatherers. The range of costs and benefits is rather nebulous at this time. Indications are that if sufficient attention is paid to the organization of markets in addition to organization of collectors this subproject also has potential for success.

The scenarios examined were a shutdown of the project in August 1997, an extension for two years, and some type of continuation for five years.

In the pull the plug case, only Chobe and Sankuyo would survive as a wildlife activity. KDT work on Cochineal would continue as they have some sustainability, are not completely dependent on USAID funds and they are well on the way to market. All other activities would collapse and poison the wells for any other donor to do follow on. For this scenario the costs and benefits of Chobe and KDT were continued and all else written off.

The benefits off the two year extension case were flat lined at present levels for Chobe and up to estimated production levels for those in startup, after which they were also flat lined. The two year extension case would allow no new activity, but should allow sub-projects now in the gate to at least get started.

A five year extension, or phase 2, or new activity rooted in the solid base of community work of NRMP, would allow the spread effect to kick in and increase the return to the investment already expended.  In this case activities are replicated until year 2002 at which point all the relatively easy community projects would be in place. and all community wildlife management projects would be in place.  The cochineal sub-project was not replicated as this type of very high value niche is limited.  The other activities were used as illustrative of the type of returns that could be expected from further activity.

The time line chosen is fifty years. For sustainable natural resources this is a conservative time frame. Shorter time lines could have been chosen but would require resource salvage value calculations that would result in roughly the same values.

On the costs side of the equation The cost s to USAID from the NGO cooperative agreement, the Chemonics contract, AID direct costs, were included along with the costs of the government of Botswana. These were not audited costs, in several cases they are estimated costs.

Results

|  | Millions US Dollars |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Options | Investment | Additional Investment | Return | Internal rate of return | Benefit cost ratio |
| end project | $19.89 |  | $50.39 | 5.60% | 2.5 |
|  |  | $4.79 |  |  |  |
| two year extension | $24.68 |  | $70.98 | 6.90% | 2.9 |
|  |  | $5.54 |  |  |  |
| 5 year extension | $30.22 |  | $167.08 | 10.34% | 5.5 |

Table___ Community benefits only, no secondary benefits, no indirect benefits, no district government benefits, no individual benefits, no reinvestment benefits.

The internal rates of return of the analysis are seen in table___ . The two year and the five year cases are more than acceptable for a private sector venture considering the conservatism of the analysis.  Considering that it is a bilateral aid project housed in a government agency, it is astounding.  However, the two year case is still picking the fruit before it is ripe.

The Internal Rate of Return is a poor measure for development. It is the return on the investment over time. A better measure for development is the Benefit Cost ratio. If this ratio is greater than one, It means that the project has at least covered its cost by generating returns. In the case of the two year extension it generated benefits totaling 2.9 times greater than the costs. The five year extension generated 5.5 times more benefits than costs.

The analysis is most sensitive to change in the cochineal price which in the past seven years has varied from $23 to $170 per kilo. This can vary the IRRs as follows

Worst case Midpoint    Best case

No extension   	0.6%	        10.4%       11.6%

2 year extension	2.9%	        11.6%       12.8%

5 year extension	8.0%	        13.7%       14.7%

Graph___Community benefits only, no secondary benefits, no indirect benefits, no district government benefits, no individual benefits, no reinvestment benefits.

Some of the nonquantifiable benefits not included in the analysis include:

#	esthetic

#	cross cultural

#	pride of ownership

#	acquisition of skills

#	increase of living standards

#	jobs

#	increase in foreign exchange earnings

#	community awareness

#	community empowerment

#	access to land

#	capacity to deal with management of problems

#	economic diversification

#	increased local governance capacity

#	stable natural resource base

Conclusion: Over the economic time frame, project investment in community resource management capacity will have economic and financial benefits far exceeding breakeven for the investment made by USAID and other donors. In addition this capacity may be used in other non-resource based sectors of the economy and the society to further advance rural people. From the view point of benefits to rural poor the extension of five years makes the most sense. From the point of view of consolidation of investment and economic efficiency a five year extension makes the most sense.  From the point of view of balance of payments, and  economic stability a five year extension is the best choice.

Recommendations: There is need for a detailed cost benefit analysis from the producers (resource user community) view point.  This will point out incentives, sensitive variables, and possible policy needs, and can be used as a tool for the management of the resources.

Extend the project for at least five years. More important than the sustainability of present communities activities is the sustainability of the process that enable communities to undertake these activities.

Regional Economic Aspects

There is no question about the regionality of this project. The entire gamut of project activities including veld products, wildlife harvesting, and tourism, produce returns from across national borders. All of these products and services are exported.  Tourism is an export sector. Veld products markets including carmine dye, Marula fruit products, bottled water for tourists, and even Mopane caterpillars, are across borders and produce foreign exchange.   Probably less than 10% of project economic benefits are local origin. With this in mind, one of the major areas that RCSA could address is assistance in organization of the regional tourism industry. Regional solidarity and pooling of marketing in regional tourism circuits would do much more for the economies of Southern African states than many so called development activities.

Annex 4: Partial List of Contacts

Government of Botswana

Ministry of Commerce and Industry

Tswelopele C. Moremi	Permanent Secretary

Department of Wildlife and National Parks

S.C. Modise			Director, DWNP

Ms. Pelaelo			Assistant Director of Personnel, DPSM

Mrs. Pelani			Assistant Director of Administration, DWNP

Mr. Kgoberego Nkawana		Principal Game Warden, DWNP (Conservation Education)

Mr. B. S. Pheto			Principal Administrative Officer, DWNP

Mr. Moemi Batshabang		Game Warden, DWNP (Conservation Education)

Mr. Unaugone Bulayani		Temporary Game Scout, DWNP-Gaborone Game Reserve

Mr. Duncan Keabetsue		Senior Game Scout, Molepolole

Mr  M. J. Ketihoilwe		Environmental Education Officer, Mokolodi

Dr. David Lawson		Principal Game Warden, DWNP (M & U)

Mr. Innocent Magole		Senior Game Warden, DWNP (Parks)

Ms. Rapelang Masogo		Senior Biologist, DWNP (Research)

Mr. Tom Modisane		Game Warden, Kweneng District

Ms. Poppy Monyatsi		Principal Game Warden, DWNP (M & U)

Ms. Selebaleng Morubana		Senior Administrative Officer, DWNP (M & U)

Ms. Muaseretse Seitshiro		Senior Administration Officer, DWNP (M & U)

Mr. O. T. Thakadu		Game Warden Community Extension, DWNP (M & U)

Mr. Isaac Theophilus		Principal Game Warden, DWNP (M & U)

Ms. Magdelene Tshupeng		Game Scout, Gaborone Game Reserve

Mr. David Shannon		Organizational Development Advisor, ODA

Mr. Julius Mangubuli		Principal, BWTI

Ms. Mary Kalikawe		Deputy Principal, BWTI

Mr. Rex Mokandla		Training Officer, BWTI

Mr. Steve Sekhute		Training Officer, BWTI

Ms. D. Gopolong			Principal Administrative Officer, DPSM

Ms. Mokosi			Assistant Director of Training, DPSM

Ms. Mulalo			Principal Administrative Officer Recruitment, DPSM

Mr. K. O. Mpuan			Senior Personnel Officer, DPSM

Ministry of Finance and Development Planning

M. Ngidi			Deputy Secretary for Economic Affairs

Joyce Anderson 			MFDP/RDCD (rural development coordinating department)

C.K. Dekop			MFDP

Robinson Dimbungu		District, Council Economic Planner

Amos Hubago			District, Assistant Economic Planner

Zenzile Saul			District, Assistant Economic Planner

Basipo Madandume		District, Assistant Economic Planner

Ministry of Local Government, Lands and Housing

Victor Rantshabeng		Director, Department of Lands

Soblem Mayane			District Commissioner, Chobe

S.S. Maroba			SLO-LU/ Dept. of  Lands

Mr. Ntingana 			Tawana Land Board, Community lands Lease Officer

Ian Tema			District, Senior Lands Officer

Ministry of Agriculture

Raymond Kwerepe		Principal Range Ecologist

Dipholo K.P. Dipholo		Secretary, Agricuture Resources Board

N. Manyothwane			Senior Agric. Economist

E.B. Karkari			Senior Agric. Economist

Ministry of Education

Mrs. F. Leburu-Sianga		Principal Education Officer, CDD/MoE

Conservation International

Karen Ross			Director, Okavango Project

Natural Resources Management Project

Chemonics International Staff

Mr. Nicholas Winer		Chief of Party, NRMP

Ms. Laura Vinoly			Administration Specialist

Mr. Gary Clark			HRDU Advisor for NRMP

Dr. Bill Kelly			BWTI Advisor, Chemonics

Mr. Wilf Slade			Non-Formal/Conservation Education Advisor

Michael Painter			Monitoring and Evaluation Specialist

Jonathon Habarad		Sociologist

Mark Johnstad			CBNRM Policy Specialist

Conservation International

John Hazam			Senior Extension Officer

Domestic Technologies International

Mr. Pete Hancock		BWTI Instructor

Mr. John Lubrook		Community Extension Specialist

Mr. Frank Potts			BWTI Instructor

Richard Hartley			Resource Economist

PACT

Mr. Daniel Walz			Director, IRCE

Morongwe Ntloedibe-Disele	IRCE Facilitator

Mr. Khulikani Mpofu		IRCE Facilitator

Non-governmental organization and private sector

Modisa Mothoagae		Director, HATAB

Mr. Tony Johnson		Business Advisor, Maun Business Training Center

Jacob Tshweneyagae		Training Manager, Maun Business Training Center

Ms. Ketsile Molokomme		Training Officer, CORDE

Mr. Wazma Tema		Education Officer, KCS

Dr Keith Leggett 			Kalahari Conservation Society

Joyce Thobega			General Manager Women's Finance House Botswana

Vivian Mazunga			BACONGO

G Phorano			General manager Thusano Lefatsheng

Richard Kashweeka		FONSAG

Frank Taylor			Veld Product Research

Charlie Motshubi 		DWNP

Mr. Sebina			Education Officer, NCS

Daisy Wright 			Game Safaris

Lloyd Wilmore			WL Tourism Operator

Other donor representative and international organizations

Ruud Jansen			IUCN

Paula Chalinder			ODA

Britt Hilde Kjoelaas		Royal Norwegian Embassy

James Aitken			LTS International, Ltd.

Jan Isaksen			Executive Director, BIDPA

Mr. Makweetsi Masisi		Assistant Project Officer/Education, UNICEF

Heli Perret 			IFAD consultant

Mr. James Carney		Consultant, NLT Institute

Ms. Candace Conrad		Senior Vice President Africa, Chemonics

Ms. Christine Elias		Senior Associate Africa Progam, World Resources Institute

Ms. Roshana Lite			Project Assistant Africa, Chemonics

Ms. Leslie Mitchell		Director, PACT Washington

Mr. Asif M. Shaikh		President & CEO, International Resources Group

Mr. Anthony Pryor		USAID AFR/SD/PSGE

Annex 5:  Selected References

University of Botswana, PRA: Contract and Commitment for Village Development, Report on the MFDPs Participatory Rural Appraisal Pilot Project., 1996.

Batshabang, M and W. Slade, 1996. Trip Reports for Molepolole, Ghanzi, Tshabong, and Maun. NRMP/GOB.

Brown, A. et al. 1991. A Proposed Programme of Training and Related Management. Chemonics International.

Cantrell, M. and M. Nganunu (eds.). 1992. Environmental Education in Botswana: An National Planning Conference. Oct. 7-11, 1991. Government of Botswana/University of Botswana/Kalahari Conservation Society.

Fiebig, W. 1996. Development of the Botswana NRMP: Review of Results Report and Draft Results Framework.

Kupaza, R. 1996. (ed). Professional Enhancement Seminar 15-19 April, 1996. BWTI.

NRMP/GOB, 1996. Consultancy Report: Skills and Knowledge Training and Development at BWTI.  Training of Trainers Programme. Nov. 27, 1995.

NRMP/GOB, 1996. Project Summary Sheet

NRMP/GOB. 1995. Consultancy Report: Status of Environmental Education Activities in the Botswana Ministry of Education.

NRMP/DWNP. 1995. Training Needs Analysis. Oct. 1995

NRMP/DWNP. 1995. Botswana Wildlife Training Institute Curriculum: Induction Basic Training and the National Certificate in Wildlife Management and Conservation.  Nov. 1995, 1st Edition.

NRMP/GOB, 1993. Supplement to Amplified Project Description. Personnel Planning and Training Component. USAID.

NRMP, 1993. Strengthening DWNP's Extension Role and Capacity: A Report to DWNP. June 1993.

NRMP/GOB, 1992. The Formal Sector Environmental Education Needs Assessment.  A Summation of Teacher and Teacher Educator Responses.  Volume 1 and 2.

NRMP/GOB, 1993. The Non-Formal Education Sector Evironmental Education Needs Assessment.  Extension Educators' and Literacy Assistants' Responses to an Environmental Education Needs Assessment Questionnaire. (Draft document).

Reed, J. 1995. Natural Resources Management Project End of Contract Report. Environmental Education Advisor. NRMP/USAID.

Shaikh, A. 1996. Analysis of the Strategic Objectives Linkages for the Botswana Component of NRMP.  WRI/IRG

Winer, N. 1995. A Botswana Case Study: Conservation Through Community Action The Chobe Enclave.

USAID. 1993. Midterm Evaluation of the Botswana Natural Resources Management Project

NRMP. Veld Products, Wildlife, and Communities in Botswana.  Brochure

Natural Resources Management Project, Annual Workplan, 1994

Natural Resources Management Project, Annual Workplan, 1995

Natural Resources Management Project, Annual Workplan, 1996

The Contribution of Community-Based Wildlife Tourism to Botswana, 1996

Project Summary Sheet, September 1996

A Botswana Case Study, Conservation through community action- The Chobe Enclave

The Natural Resources Management Project, Briefing Notes, April 1996

DWNP. 1994.  Status of selected wildlife resources in Botswana and recommendations for conservation actions.

GOB.  1968. Tribal Land Act

GOB. 1991.  Tourism Regulations

GOB. 1992.  Wildlife Conservation and National Parks Act

GOB. 1986.  Wildlife Conservation Policy

GOB. 1990.  Tourism Policy

NRMP. 1992.  Terms of Reference for the Ngamiland WMA management plans

?However, the relationship is changing.  In the National Development Plan 8 that will come out shortly, the GOB aims to develop partnerships between itself and communities.  Those communities that demonstrate commitment to helping themselves will be favored in receiving resources.

?One of these grants went directly to the NGO Thusano Lefatsheng as a revolving fund for collection of grapple.

?In particular, the marula collection, processing and marketing studies which were managed by NRMP technical advisors involving the Gweta Trust and evaluated by IRCE.